## Guidance on the document
This document is the 'Action Plan' element of our Digitalisation Strategy & Action Plan. It should be reviewed in conjunction with our published strategy. The commitments in this plan link back to the strategy document for ease of reading
The strategy will be updated every 2 years as a minimum with a 6 monthly update of progress against the plan and any additions
The plan includes a Gantt Chart for ease of use. Planned or in progress tasks are in blue, completed are green and tasks at risk of delivery on target are in amber for transparency
In addition to the colour coding of the Gantt chart, we also include text to inform readers of progress. There will be a column of text for every 6 month period for ease of tracking progress over time
Additional tasks added through our ongoing stakeholder engagament will be highlighted as 'new' in the relevant period update
We welcome any feedback, good or bad to inform and shape future versions of our strategy and plan
Any queries or feedback can be directed to Ian.Dunstan@wwutilities.co.uk

## The WWU Plan
|  |  | 2021 | [11 empty] | 2022
Commitment | Key deliverables | Jan - Jun 2021 6 monthly progress update | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Ongoing consultation on strategy and plan | Publish strategy and inform stakeholders | Completed | bar: 2021 Jan; 2022 Dec
| Digitalisation specific engagement events | A number of engagement events are planned to inform the next strategy update | bar: 2021 Jul to 2021 Sep; 2022 Jul to 2022 Sep
| Receive and review feedback | We are in constant touch with stakeholders on their data needs. There are a number of new lines added to the plan as a result of stakeholder feedback to date
2. Upgrade our core asset repository and finance systems | Complete future system design | Complete | bar: 2021 Jan to 2021 Feb
| Build phase of new system | Build is underway with a large team of IT and Business experts supporting. We are currently reviewing complexity to ensure delivery risk is minimised whilst still delivering the improvements and ambitions of ourselves and our stakeholders | bar: 2021 Jan to 2021 Dec
| Data migration | Over 1million records have been reviewed and many thousands improved in readiness for data migration | bar: 2021 Jan to 2021 Dec
| Cutover to new system | April saw the launch of our new Customer Experience (CX) system. This is already helping us to serve our customers more effectively and efficiently than ever before. Next phase, before the busy winter period, we are prioritising changes to our Emergency & Repair systems and processes with the introduction of a new smart App for Operational colleagues. Changes will be accompanied by the roll out of new iPad’s, replacing outdated CF19 devices | bar: 2021 Oct to 2022 Feb
3. Digitise remaining asset data sets | Complete Service Governor surveys and digitisation programme | Physical surveys complete but impacted by covid. Currently updating our GIS system and asset repository. New app built to improve survey process for future condition surveys. HSE have reviewed app and fedback | bar: 2021 Jan to 2021 Mar
| Cathodic Protection Systems digitised and mapped to assets | HP system in Wales digitised and currently collecting data from Operational colleagues in the South West | bar: 2021 Apr to 2021 Aug
| Multi-Occupancy Building (MOBs) moved from standalone databases to core asset repository | High rise data prepared awaiting migration process to new SAP | bar: 2021 Jan to 2021 Aug
4. Internet of Things (IoT) | Innovation project on trial sites to explore sensors, remote monitoring and remote maintenance technologies | ICS Project completed with ICS consultancy using existing data to flag gaps that could be filled by sensor technology. Considering a phase II project on 2 PRI sites | bar: 2021 Apr to 2021 Dec
| Delivery of remote pressure control at test sites as part of project Optinet | Complete | bar: 2021 Jan to 2021 May
| Develop a strategy and plan for sensors and monitoring | Virtual team of operational; Asset And IT people assesmbled | bar: 2021 Sep to 2022 Apr
| Deliver phase 1 of the IoT plan | Not started | bar: 2022 May to 2022 Dec
| Derive GD3 IoT plan | Not started | bar: 2022 Oct to 2022 Dec
5. Publish a metadata catalogue | Derive 1st catalogue based on stakeholder themes | A catalogue of data and publications has been developed and we are currently designing version 2 | bar: 2021 Jan to 2021 Mar
| Publish on our website and inform stakeholders | Complete | bar: 2021 Apr
| Publish further links to key data sets and analysis | These are detailed as new lines at the bottom of this page | bar: 2021 Apr; 2021 Oct to 2021 Nov; 2022 Apr to 2022 May; 2022 Oct to 2022 Nov
| 6 monthly review and update to metadata catalogue | Under review | bar: 2021 Oct to 2021 Nov; 2022 Apr to 2022 May; 2022 Oct to 2022 Nov
6. Pathfinder | Use of Pathfinder in a number of projects including:
| Milford Haven Energy Kingdom - Innovate UK project | Project pushed back due to delay in other areas | bar: 2021 Jan to 2022 May
| EPIC - West of England Combined Authority (tbc) | Project in progress. Currently supporting data provision for whole system CBA use
| Zero 2050 - South Wales Decarbonisation planning | Complete | bar: 2021 Jan to 2021 Mar
| Zero 2050 - South Wales Decarbonisation roll out to the rest of Wales (TBC) | Plan under review | 2021 Jun: TBC
| Gas Goes Green workstream 1.3 local, regional & mational pathways studies | Corrected to 1.3 (was shown as 1.4) | bar: 2021 Jan to 2021 Oct
| Engage on further projects and use cases | Updates are detailed as new lines at the bottom of this page
7. Priority Services Register (PSR) | Productionalise PSR data on maps to help plan projects | Currently developing a detailed plan | bar: 2021 Jan to 2021 Jul
| Resolve GDPR issus over use of PSR data in maps | Currently developing a detailed plan | bar: 2021 Apr to 2021 Oct
| Innovation project to add ONS and licenced data on demographics to further support planning | Reviewed Warm Wales (Fresh) data. Sample sets taken | bar: 2021 Apr to 2022 Apr
| Build analytic tools to use the data and drive communciation plans and target projects and campaigns | ARCGIS reviewed - new improved mapping data contract to improves ease of data access to 3rd parties | bar: 2021 Apr to 2022 Apr
8. National map | Actively participate in ENA subgroup PoC | We have a representative on the project team. We have shared the required data and are in the process of signing the licence agreement for data use | bar: 2021 Jan to 2021 Dec
| Develop system to seemlessly publish data to the national map | We have easy access to GIS data through use of a new GIS system | bar: 2021 Oct to 2022 Mar
| Productionalise national map and increase data sets available | Not started. Will be driven by learning from the PoC | bar: 2022 Apr to 2022 Dec
9. Create a dedicated data and analytics team | GD2 Business restructure | Complete | bar: 2021 Jan to 2021 Mar
| Populate data and analytics team | Team built but some members are involved in our SAP upgrade and won't join the team until year end. Analytics offering under development | bar: 2021 Apr to 2021 Sep
| Implement new data triage process | Process through ENA adopted within WWU. We have a representative on the ENA data trige subgroup reviewing success and managing future improvements | bar: 2021 Jul to 2021 Sep
| Publish methods for external stakeholders to engage | Done via ENA currently | bar: 2021 Oct
10. Sharing future data sets | Gas goes green - green gas data reporting through ENA | Proposals discussed with GGG Advisory Group in June 2021 | bar: 2021 Jun; 2021 Dec; 2022 Jun; 2022 Nov
| Publish detailed environmental performance data | This will be published with RRP by 31st July | bar: 2021 Jun to 2021 Aug; 2022 Jun to 2022 Aug
| Publish heat and hot water ready reckoner | This is complete | bar: 2021 Apr to 2021 May
New: Whole System CBA tool | Promote and support use of Whole System Cost Benefit Analysis tool developed as part of Open Network | This is a new line item added in this period. One of our team co-led the project to create the tool. Currently suppoting various innoavtion projects and other use cases | bar: 2021 Jun to 2022 Mar
New: Flexible Generation Forecaster | Flexible Generation Forecaster for real time developed as part of a WWU led innovation project: https://www.smarternetworks.org/project/nia_wwu_068 | This is a new line item added in this period. This is now complete | bar: 2021 Jan to 2021 May
| Agree mechanism to share Flexble Generation Forecaster wth project partners | Under review | bar: 2021 Jun to 2021 Jul
| Share Flexible Generation Forecaster with non-funding parties (tbc) | Under review | bar: 2021 Jul to 2022 Dec
New: Pathfinder Lite | Development of Pathfinder Lite as part of Innovate UK Project: Bank Energi | This is a new line item added in this period. This is now complete | bar: 2021 Jan to 2021 May
| Agree mechanism to share Pathfinder Lite | Under review | bar: 2021 Jun to 2021 Jul
| Use of Pathfinder Lite by additional parties (tbc) | Under review | bar: 2021 Aug to 2022 Dec
New: NUAR | NUAR is now coming to Wales | We have held a number of meetings with the NUAR team and will share the plan in the next update