## Totex Costs Summary
Regulatory Reporting Pack
Wales and West
2014/15
2.2 Summary of totex costs
Current year RRP submission - £m
2014/15 prices
| Current year actuals | Forecast
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 8.6522 | 6.3611 | 9.7308 | 10.8373 | 8.5838 | 4.363 | 4.3165 | 4.3928 | 57.2375
Connections | 10.4858 | 9.517 | 12.8 | 12.85 | 12.8 | 11.9 | 11.1 | 11.3 | 92.7528
Mains Reinforcement | 3.8596 | 3.5024 | 4.1634 | 3.1918 | 3.1918 | 3.1918 | 3.1918 | 3.1918 | 27.4842
Governors (Replacement) | 2.3128 | 2.1267 | 3.0708 | 2.4221 | 2.4221 | 2.4221 | 2.4436 | 2.5081 | 19.7282
Other Capex | 26.7133 | 21.8051 | 18.3044 | 15.1289 | 15.3635 | 19.3645 | 21.0864 | 19.082 | 156.8481
of which IT | 5.5752 | 7.5648 | 7.6573 | 6.34 | 6.0925 | 5.8255 | 6.022 | 5.572 | 50.6494
of which Vehicles | 5.336 | 5.2813 | 5.2832 | 4.5005 | 4.0846 | 4.673 | 6.8057 | 6.9057 | 42.8699
Total Capex | 52.0237 | 43.3124 | 48.0694 | 44.4301 | 42.3611 | 41.2414 | 42.1383 | 40.4747 | 354.0509
HSE driven mains & services | 65.7937 | 59.1838 | 68.243 | 66.2068 | 65.384 | 64.9381 | 64.3839 | 63.6577 | 517.791
Non-HSE driven mains & services | 6.1473 | 15.7456 | 8.1402 | 8.116 | 7.2152 | 7.2004 | 7.2418 | 7.2896 | 67.0961
Risers | 1.5427 | 2.4898 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 9.1325
Total Repex | 73.4836 | 77.4192 | 77.2332 | 75.1729 | 73.4492 | 72.9885 | 72.4757 | 71.7974 | 594.0196
Work Management | 23.1457 | 20.2569 | 21.6644 | 21.5753 | 21.0966 | 20.7142 | 20.8714 | 20.5214 | 169.846
Emergency | 10.0042 | 10.311 | 11.4356 | 12.0388 | 12.458 | 12.0907 | 12.2439 | 12.2406 | 92.8228
Repair | 9.8067 | 9.8773 | 10.8994 | 11.4743 | 11.8738 | 11.5238 | 11.6698 | 11.6667 | 88.7919
Maintenance | 14.4365 | 17.7974 | 17.0124 | 17.5968 | 18.0028 | 17.647 | 17.7954 | 17.7922 | 138.0804
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Activities | 19.5129 | 13.7144 | 9.1149 | 10.0332 | 9.5268 | 9.6555 | 9.7219 | 9.6602 | 90.94
of which xoserve | 4.1288 | 4.235 | 4.9359 | 5.4054 | 4.5088 | 4.4895 | 4.5235 | 4.45 | 36.6768
Total Direct Opex | 76.906 | 71.9571 | 70.1266 | 72.7185 | 72.958 | 71.6313 | 72.3024 | 71.8812 | 580.4811
Business support | 16.3815 | 15.9439 | 16.6164 | 17.8568 | 18.827 | 19.5785 | 20.1044 | 20.6773 | 145.9859
Training & Apprentices | 1.9347 | 1.7895 | 2.1209 | 2.721 | 3.5631 | 4.2083 | 4.3122 | 4.3177 | 24.9674
Total Indirect Opex | 18.3162 | 17.7334 | 18.7373 | 20.5778 | 22.3901 | 23.7869 | 24.4166 | 24.995 | 170.9533
Total Opex | 95.2222 | 89.6905 | 88.8639 | 93.2963 | 95.3481 | 95.4182 | 96.719 | 96.8761 | 751.4343
Of which total sub-deducts | 0 | 0 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.3
Total Controllable costs | 220.7294 | 210.4221 | 214.1665 | 212.8993 | 211.1584 | 209.6481 | 211.3329 | 209.1481 | 1699.5048
Non-Controllable costs
Licence/network/other | 40.2798 | 40.8551 | 38.3286 | 40.7286 | 40.7286 | 40.7286 | 40.7286 | 33.8286 | 316.2064
NTS exit costs | 21.1676 | 22.9279 | 19.5334 | 19.5334 | 19.5334 | 19.5334 | 19.5334 | 19.5334 | 161.296
Shrinkage | 9.0852 | 6.7603 | 5.704 | 5.704 | 5.704 | 5.704 | 5.704 | 5.704 | 50.0695
NTS pensions contributions | 4.6247 | 4.6999 | 4.6718 | 4.6718 | 4.6718 | 4.6718 | 4.6718 | 4.6718 | 37.3555
Total non-controllable costs | 75.1572 | 75.2432 | 68.2379 | 70.6379 | 70.6379 | 70.6379 | 70.6379 | 63.7379 | 564.9275
Total funded costs - including uncertainties | 295.8867 | 285.6653 | 282.4044 | 283.5371 | 281.7962 | 280.2859 | 281.9708 | 272.886 | 2264.4323
Of which: uncertainties*:
Smart metering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Streetworks | 1.7686 | 1.1535 | 0.025 | 0.175 | 0.475 | 0.825 | 1.275 | 1.55 | 7.2471
Physical Security Upgrade Programme (PSUP) | 0 | 0.96294 | 0.9 | 2.8 | 3.2 | 0 | 0 | 0 | 7.8629
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total uncertainties* | 1.7686 | 2.1165 | 0.925 | 2.975 | 3.675 | 0.825 | 1.275 | 1.55 | 15.1101
Total funded costs - excluding uncertainties* | 294.1181 | 283.5488 | 281.4794 | 280.5621 | 278.1212 | 279.4609 | 280.6958 | 271.336 | 2249.3223
Previous year RRP submission - £m | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
2014/15 prices
Previous year forecast
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 8.6522 | 8.0701 | 13.9521 | 13.3312 | 9.8925 | 10.5234 | 9.4835 | 8.0071 | 81.912 | LTS, storage and entry | 0 | -1.7089 | -4.2214 | -2.4939 | -1.3087 | -6.1604 | -5.1669 | -3.6142 | -24.6745 | LTS, storage and entry | 0% | -21.18% | -30.26% | -18.71% | -13.23% | -58.54% | -54.48% | -45.14% | -30.12%
Connections | 10.4858 | 9.9364 | 11.039 | 12.2468 | 12.086 | 12.4883 | 12.6243 | 12.6407 | 93.5473 | Connections | 0 | -0.41935 | 1.761 | 0.60323 | 0.714 | -0.58833 | -1.5243 | -1.3407 | -0.79451 | Connections | 0% | -4.22% | 15.95% | 4.926% | 5.908% | -4.711% | -12.07% | -10.61% | -0.8493%
Mains Reinforcement | 3.8596 | 3.0707 | 3.3482 | 3.4688 | 3.4982 | 3.5329 | 3.5664 | 3.5839 | 27.9287 | Mains Reinforcement | 0 | 0.43173 | 0.81516 | -0.277 | -0.30639 | -0.34115 | -0.37465 | -0.39216 | -0.44447 | Mains Reinforcement | 0% | 14.06% | 24.35% | -7.986% | -8.759% | -9.656% | -10.5% | -10.94% | -1.591%
Governors (Replacement) | 2.3128 | 3.0418 | 4.3471 | 4.5212 | 4.4246 | 4.4685 | 4.5105 | 4.545 | 32.1714 | Governors (Replacement) | 0 | -0.9151 | -1.2763 | -2.0991 | -2.0025 | -2.0465 | -2.0669 | -2.0368 | -12.4432 | Governors (Replacement) | 0% | -30.08% | -29.36% | -46.43% | -45.26% | -45.8% | -45.82% | -44.82% | -38.68%
Other Capex | 26.7133 | 24.5575 | 15.7083 | 13.9473 | 12.7088 | 12.8433 | 17.5987 | 16.1969 | 140.2741 | Other Capex | 0 | -2.7524 | 2.5961 | 1.1816 | 2.6547 | 6.5212 | 3.4877 | 2.885 | 16.574 | Other Capex | 0% | -11.21% | 16.53% | 8.472% | 20.89% | 50.78% | 19.82% | 17.81% | 11.82%
of which IT | 5.5752 | 7.3749 | 5.9927 | 6.0725 | 7.5223 | 7.2515 | 7.4653 | 6.6502 | 53.9047 | of which IT | 0 | 0.18996 | 1.6646 | 0.26751 | -1.4298 | -1.426 | -1.4433 | -1.0782 | -3.2553 | of which IT | 0% | 2.576% | 27.78% | 4.405% | -19.01% | -19.66% | -19.33% | -16.21% | -6.039%
of which Vehicles | 5.336 | 9.4492 | 5.8624 | 5.01 | 2.811 | 2.9808 | 7.6847 | 7.4611 | 46.5952 | of which Vehicles | 0 | -4.1679 | -0.57925 | -0.50947 | 1.2736 | 1.6922 | -0.87903 | -0.5554 | -3.7253 | of which Vehicles | 0% | -44.11% | -9.881% | -10.17% | 45.31% | 56.77% | -11.44% | -7.444% | -7.995%
Total Capex | 52.0237 | 48.6764 | 48.3948 | 47.5152 | 42.6101 | 43.8565 | 47.7833 | 44.9736 | 375.8335 | Total Capex | 0 | -5.3641 | -0.32538 | -3.0851 | -0.24899 | -2.6151 | -5.6451 | -4.4989 | -21.7827 | Total Capex | 0% | -11.02% | -0.6724% | -6.493% | -0.5843% | -5.963% | -11.81% | -10% | -5.796%
HSE driven mains & services | 65.7937 | 77.2801 | 77.9429 | 78.3054 | 77.6937 | 77.1655 | 76.5611 | 80.352 | 611.0943 | HSE driven mains & services | 0 | -18.0963 | -9.6999 | -12.0986 | -12.3097 | -12.2274 | -12.1772 | -16.6943 | -93.3033 | HSE driven mains & services | 0% | -23.42% | -12.44% | -15.45% | -15.84% | -15.85% | -15.91% | -20.78% | -15.27%
Non-HSE driven mains & services | 6.1473 | 8.1481 | 9.0884 | 9.5582 | 9.7696 | 9.5379 | 9.2915 | 8.9968 | 70.5377 | Non-HSE driven mains & services | 0 | 7.5975 | -0.94819 | -1.4421 | -2.5544 | -2.3375 | -2.0498 | -1.7072 | -3.4416 | Non-HSE driven mains & services | 0% | 93.24% | -10.43% | -15.09% | -26.15% | -24.51% | -22.06% | -18.98% | -4.879%
Multi occupancy buildings (MoBs) | 1.5427 | 0.61804 | 0.52534 | 0.49443 | 0.40173 | 0.37083 | 0.37083 | 0.36002 | 4.6839 | Multi occupancy buildings (MoBs) | 0 | 1.8718 | 0.32466 | 0.35557 | 0.44827 | 0.47917 | 0.47917 | 0.48998 | 4.4486 | Multi occupancy buildings (MoBs) | 0% | 302.9% | 61.8% | 71.91% | 111.6% | 129.2% | 129.2% | 136.1% | 94.98%
Total Repex | 73.4836 | 86.0462 | 87.5566 | 88.358 | 87.865 | 87.0742 | 86.2235 | 89.7088 | 687.7649 | Total Repex | 0 | -8.627 | -10.3234 | -13.1851 | -14.4158 | -14.0857 | -13.7478 | -17.9114 | -93.7453 | Total Repex | 0% | -10.03% | -11.79% | -14.92% | -16.41% | -16.18% | -15.94% | -19.97% | -13.63%
Work Management | 23.1457 | 22.1502 | 23.6574 | 23.3511 | 23.2702 | 24.4032 | 25.1358 | 22.7308 | 187.8444 | Work Management | 0 | -1.8933 | -1.993 | -1.7758 | -2.1736 | -3.689 | -4.2643 | -2.2094 | -17.9984 | Work Management | 0% | -8.548% | -8.425% | -7.605% | -9.341% | -15.12% | -16.97% | -9.72% | -9.582%
Emergency | 10.0042 | 10.4849 | 11.9904 | 14.8815 | 15.5502 | 15.739 | 16.2419 | 16.2159 | 111.1079 | Emergency | 0 | -0.17381 | -0.5548 | -2.8427 | -3.0922 | -3.6483 | -3.998 | -3.9753 | -18.2851 | Emergency | 0% | -1.658% | -4.627% | -19.1% | -19.89% | -23.18% | -24.62% | -24.51% | -16.46%
Repair | 9.8067 | 11.7183 | 12.1897 | 13.2596 | 13.8032 | 14.2298 | 14.4082 | 14.4698 | 103.8852 | Repair | 0 | -1.841 | -1.2904 | -1.7852 | -1.9293 | -2.7059 | -2.7384 | -2.8031 | -15.0934 | Repair | 0% | -15.71% | -10.59% | -13.46% | -13.98% | -19.02% | -19.01% | -19.37% | -14.53%
Maintenance | 14.4365 | 16.0304 | 16.469 | 17.6077 | 17.9216 | 18.2404 | 18.5164 | 18.6062 | 137.8281 | Maintenance | 0 | 1.767 | 0.54346 | -0.010907 | 0.081127 | -0.59333 | -0.72098 | -0.81403 | 0.25233 | Maintenance | 0% | 11.02% | 3.3% | -0.06195% | 0.4527% | -3.253% | -3.894% | -4.375% | 0.1831%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other Direct Activities | 19.5129 | 8.7749 | 8.332 | 9.539 | 10.4337 | 9.1714 | 9.4802 | 9.7557 | 84.9998 | Other Direct Activities | 0 | 4.9395 | 0.78287 | 0.4943 | -0.90692 | 0.4841 | 0.24172 | -0.095465 | 5.9401 | Other Direct Activities | 0% | 56.29% | 9.396% | 5.182% | -8.692% | 5.278% | 2.55% | -0.9786% | 6.988%
of which xoserve | 4.1288 | 5.2313 | 4.7687 | 5.8132 | 6.6849 | 5.3968 | 5.6827 | 5.9645 | 43.671 | of which xoserve | 0 | -0.99638 | 0.16717 | -0.40775 | -2.1762 | -0.90732 | -1.1592 | -1.5145 | -6.9942 | of which xoserve | 0% | -19.05% | 3.505% | -7.014% | -32.55% | -16.81% | -20.4% | -25.39% | -16.02%
Total Direct Opex | 76.906 | 69.1587 | 72.6385 | 78.6388 | 80.9789 | 81.7837 | 83.7824 | 81.7784 | 625.6655 | Total Direct Opex | 0 | 2.7984 | -2.5119 | -5.9203 | -8.0209 | -10.1524 | -11.48 | -9.8973 | -45.1844 | Total Direct Opex | 0% | 4.046% | -3.458% | -7.528% | -9.905% | -12.41% | -13.7% | -12.1% | -7.222%
Business support | 16.3815 | 19.4452 | 19.7424 | 20.0017 | 20.8232 | 21.6526 | 22.2624 | 22.5152 | 162.8243 | Business support | 0 | -3.5013 | -3.126 | -2.1449 | -1.9963 | -2.0741 | -2.158 | -1.8379 | -16.8384 | Business support | 0% | -18.01% | -15.83% | -10.72% | -9.587% | -9.579% | -9.693% | -8.163% | -10.34%
Training & Apprentices | 1.9347 | 2.5421 | 2.6737 | 2.496 | 2.5202 | 2.635 | 2.5583 | 2.6612 | 20.0211 | Training & Apprentices | 0 | -0.75252 | -0.55282 | 0.22507 | 1.0429 | 1.5733 | 1.7539 | 1.6565 | 4.9463 | Training & Apprentices | 0% | -29.6% | -20.68% | 9.017% | 41.38% | 59.71% | 68.56% | 62.25% | 24.71%
Total Indirect Opex | 18.3162 | 21.9872 | 22.4161 | 22.4977 | 23.3434 | 24.2876 | 24.8207 | 25.1764 | 182.8454 | Total Indirect Opex | 0 | -4.2538 | -3.6788 | -1.9199 | -0.95334 | -0.50074 | -0.40412 | -0.18145 | -11.8921 | Total Indirect Opex | 0% | -19.35% | -16.41% | -8.534% | -4.084% | -2.062% | -1.628% | -0.7207% | -6.504%
Total Opex | 95.2222 | 91.1459 | 95.0546 | 101.1365 | 104.3223 | 106.0714 | 108.6031 | 106.9548 | 809.9598 | Total Opex | 0 | -1.4554 | -6.1907 | -7.8401 | -8.9743 | -10.6532 | -11.8842 | -10.0787 | -58.5255 | Total Opex | 0% | -1.597% | -6.513% | -7.752% | -8.602% | -10.04% | -10.94% | -9.423% | -7.226%
Total sub-deducts | 0 | 0.31776 | 0.41134 | 0.39936 | 0.48466 | 0.47054 | 0.5482 | 0.26612 | 2.898 | Total sub-deducts | [9 empty] | Total sub-deducts | #DIV/0! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total Controllable costs | 220.7294 | 225.8686 | 231.006 | 237.0097 | 234.7974 | 237.002 | 242.61 | 241.6372 | 1873.5583 | Total Controllable costs | 0 | -15.4465 | -16.8395 | -24.1104 | -23.6391 | -27.3539 | -31.277 | -32.4891 | -174.0535 | Total Controllable costs | 0% | -6.839% | -7.29% | -10.17% | -10.07% | -11.54% | -12.89% | -13.45% | -9.29%
Non-Controllable costs | [9 empty] | Non-Controllable costs | [9 empty] | Non-Controllable costs | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Licence/network/other | 40.2798 | 27.977 | 28.0777 | 28.0777 | 28.0777 | 28.0777 | 28.0777 | 28.0777 | 236.7232 | Licence/network/other | 0 | 12.8781 | 10.2509 | 12.6509 | 12.6509 | 12.6509 | 12.6509 | 5.7509 | 79.4832 | Licence/network/other | 0% | 46.03% | 36.51% | 45.06% | 45.06% | 45.06% | 45.06% | 20.48% | 33.58%
NTS exit costs | 21.1676 | 21.7844 | 21.5977 | 22.7784 | 23.5534 | 24.1866 | 23.4822 | 22.7982 | 181.3486 | NTS exit costs | 0 | 1.1435 | -2.0643 | -3.245 | -4.02 | -4.6532 | -3.9487 | -3.2648 | -20.0526 | NTS exit costs | 0% | 5.249% | -9.558% | -14.25% | -17.07% | -19.24% | -16.82% | -14.32% | -11.06%
Shrinkage | 9.0852 | 8.5662 | 8.8404 | 8.5608 | 8.2911 | 8.0298 | 7.7555 | 7.5316 | 66.6604 | Shrinkage | 0 | -1.8059 | -3.1364 | -2.8568 | -2.5871 | -2.3258 | -2.0515 | -1.8276 | -16.5909 | Shrinkage | 0% | -21.08% | -35.48% | -33.37% | -31.2% | -28.96% | -26.45% | -24.27% | -24.89%
NTS pensions contributions | 4.6247 | 4.647 | 4.7142 | 4.7142 | 4.7142 | 4.7142 | 4.7142 | 4.7142 | 37.5571 | NTS pensions contributions | 0 | 0.052846 | -0.042393 | -0.042393 | -0.042393 | -0.042393 | -0.042393 | -0.042393 | -0.20151 | NTS pensions contributions | 0% | 1.137% | -0.8993% | -0.8993% | -0.8993% | -0.8993% | -0.8993% | -0.8993% | -0.5365%
Total non-controllable costs | 75.1572 | 62.9747 | 63.2301 | 64.1312 | 64.6364 | 65.0084 | 64.0296 | 63.1217 | 522.2893 | Total non-controllable costs | 0 | 12.2685 | 5.0078 | 6.5067 | 6.0015 | 5.6295 | 6.6083 | 0.61611 | 42.6382 | Total non-controllable costs | 0% | 19.48% | 7.92% | 10.15% | 9.285% | 8.66% | 10.32% | 0.9761% | 8.164%
Total funded costs - including uncertainties | 295.8867 | 288.8433 | 294.236 | 301.1408 | 299.4338 | 302.0104 | 306.6396 | 304.759 | 2395.8476 | Total funded costs - including uncertainties | 0 | -3.1781 | -11.8317 | -17.6037 | -17.6376 | -21.7245 | -24.6688 | -31.873 | -131.4153 | Total funded costs - including uncertainties | 0% | -1.1% | -4.021% | -5.846% | -5.89% | -7.193% | -8.045% | -10.46% | -5.485%
Of which: uncertainties*: | [9 empty] | Of which: uncertainties*: | [9 empty] | Of which: uncertainties*:
Smart metering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Smart metering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Smart metering | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Streetworks | 1.7686 | 0.1089 | 0.44508 | 0.83121 | 1.2302 | 1.503 | 1.5403 | 1.5751 | 9.0023 | Streetworks | 0 | 1.0446 | -0.42008 | -0.65621 | -0.75516 | -0.67796 | -0.2653 | -0.025077 | -1.7552 | Streetworks | 0 | 9.5923 | -0.94383 | -0.78946 | -0.61387 | -0.45108 | -0.17224 | -0.015921 | -0.19497
Physical Security Upgrade Programme (PSUP) | 0 | 1.5285 | 3.5028 | 3.4269 | 0 | 0 | 0 | 0 | 8.4582 | Physical Security Upgrade Programme (PSUP) | 0 | -0.56551 | -2.6028 | -0.62691 | 3.2 | 0 | 0 | 0 | -0.59526 | Physical Security Upgrade Programme (PSUP) | #DIV/0! | -0.36999 | -0.74306 | -0.18294 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -0.070376
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Other | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total uncertainties* | 1.7686 | 1.6374 | 3.9479 | 4.2581 | 1.2302 | 1.503 | 1.5403 | 1.5751 | 17.4605 | Total uncertainties* | 0 | 0.47911 | -3.0229 | -1.2831 | 2.4448 | -0.67796 | -0.2653 | -0.025077 | -2.3504 | Total uncertainties* | 0 | 0.29261 | -0.7657 | -0.30133 | 1.9874 | -0.45108 | -0.17224 | -0.015921 | -0.13461
Total funded costs - excluding uncertainties* | 294.1181 | 287.206 | 290.2881 | 296.8827 | 298.2037 | 300.5074 | 305.0993 | 303.1839 | 2375.4892 | Total funded costs - excluding uncertainties* | 0 | -3.6572 | -8.8088 | -16.3206 | -20.0825 | -21.0465 | -24.4035 | -31.8479 | -126.1669 | Total funded costs - excluding uncertainties* | 0 | -0.012734 | -0.030345 | -0.054973 | -0.067345 | -0.070037 | -0.079985 | -0.10504 | -0.053112
| 0 | 0 | 0 | 0 | 1.1369e-13 | 5.6843e-14 | -5.6843e-14 | 0 | 4.5475e-13
Final proposals adjusted with agreed uncertainties - £m | [9 empty] | Variance from final proposals adjusted with uncertainties | [9 empty] | % Variance from final proposals adjusted with uncertainties
2014/15 prices
| Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 16.4304 | 15.8332 | 14.2077 | 13.5569 | 15.2084 | 13.2408 | 12.2854 | 14.3547 | 115.1174 | LTS, storage and entry | -7.7782 | -9.472 | -4.4769 | -2.7196 | -6.6246 | -8.8778 | -7.9688 | -9.9619 | -57.8799 | LTS, storage and entry | -47.34% | -59.82% | -31.51% | -20.06% | -43.56% | -67.05% | -64.86% | -69.4% | -50.28%
Connections | 8.4452 | 8.6205 | 8.7293 | 8.9482 | 8.844 | 9.0492 | 9.1125 | 9.2627 | 71.0116 | Connections | 2.0406 | 0.89658 | 4.0707 | 3.9018 | 3.956 | 2.8508 | 1.9875 | 2.0373 | 21.7412 | Connections | 24.16% | 10.4% | 46.63% | 43.6% | 44.73% | 31.5% | 21.81% | 21.99% | 30.62%
Mains Reinforcement | 9.3096 | 9.3239 | 9.3362 | 9.3565 | 9.3683 | 9.3688 | 9.3717 | 9.4443 | 74.8794 | Mains Reinforcement | -5.45 | -5.8214 | -5.1728 | -6.1648 | -6.1766 | -6.1771 | -6.1799 | -6.2525 | -47.3951 | Mains Reinforcement | -58.54% | -62.44% | -55.41% | -65.89% | -65.93% | -65.93% | -65.94% | -66.2% | -63.3%
Governors (Replacement) | 2.6953 | 2.815 | 2.5739 | 3.7385 | 3.3323 | 3.3997 | 3.2144 | 3.7303 | 25.4995 | Governors (Replacement) | -0.3825 | -0.68839 | 0.4969 | -1.3165 | -0.91027 | -0.97767 | -0.77077 | -1.2222 | -5.7713 | Governors (Replacement) | -14.19% | -24.45% | 19.3% | -35.21% | -27.32% | -28.76% | -23.98% | -32.76% | -22.63%
Other Capex | 27.3908 | 25.9961 | 19.6798 | 16.2492 | 14.9237 | 14.7913 | 19.1658 | 18.5212 | 156.7179 | Other Capex | -0.67758 | -4.1909 | -1.3754 | -1.1202 | 0.43979 | 4.5733 | 1.9206 | 0.56075 | 0.13023 | Other Capex | -2.474% | -16.12% | -6.989% | -6.894% | 2.947% | 30.92% | 10.02% | 3.028% | 0.0831%
of which IT | 8.3705 | 8.0123 | 6.2434 | 5.8971 | 7.1205 | 6.759 | 6.6211 | 5.9308 | 54.9546 | of which IT | -2.7952 | -0.4475 | 1.414 | 0.4429 | -1.028 | -0.93347 | -0.59907 | -0.35876 | -4.3051 | of which IT | -33.39% | -5.585% | 22.65% | 7.511% | -14.44% | -13.81% | -9.048% | -6.049% | -7.834%
of which Vehicles | 9.026 | 7.1858 | 4.9912 | 4.5166 | 2.2311 | 2.5838 | 5.632 | 5.3851 | 41.5516 | of which Vehicles | -3.69 | -1.9045 | 0.29202 | -0.016087 | 1.8535 | 2.0892 | 1.1736 | 1.5206 | 1.3183 | of which Vehicles | -40.88% | -26.5% | 5.851% | -0.3562% | 83.08% | 80.86% | 20.84% | 28.24% | 3.173%
Total Capex | 64.2713 | 62.5886 | 54.527 | 51.8494 | 51.6768 | 49.8499 | 53.1497 | 55.3132 | 443.2258 | Total Capex | -12.2477 | -19.2762 | -6.4576 | -7.4193 | -9.3157 | -8.6085 | -11.0114 | -14.8386 | -89.1749 | Total Capex | -19.06% | -30.8% | -11.84% | -14.31% | -18.03% | -17.27% | -20.72% | -26.83% | -20.12%
HSE driven mains & services | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896 | HSE driven mains & services | 63.3041 | 59.1838 | 68.243 | 66.2068 | 65.384 | 64.9381 | 64.3839 | 63.6577 | 515.3014 | HSE driven mains & services | 2543% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 20698%
Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Non-HSE driven mains & services | 6.1473 | 15.7456 | 8.1402 | 8.116 | 7.2152 | 7.2004 | 7.2418 | 7.2896 | 67.0961 | Non-HSE driven mains & services | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Multi occupancy buildings (MoBs) | 1.5427 | 2.4898 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 9.1325 | Multi occupancy buildings (MoBs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Total Repex | 95.8606 | 93.2904 | 93.5847 | 92.9483 | 94.1844 | 94.1212 | 94.052 | 92.4816 | 750.5231 | Total Repex | -22.377 | -15.8712 | -16.3515 | -17.7754 | -20.7353 | -21.1327 | -21.5763 | -20.6842 | -156.5036 | Total Repex | -23.34% | -17.01% | -17.47% | -19.12% | -22.02% | -22.45% | -22.94% | -22.37% | -20.85%
Work Management | 22.6901 | 22.8161 | 25.0515 | 23.7029 | 22.6257 | 23.8118 | 24.1323 | 22.0928 | 186.9232 | Work Management | 0.45562 | -2.5592 | -3.3871 | -2.1276 | -1.5291 | -3.0976 | -3.2609 | -1.5714 | -17.0772 | Work Management | 2.008% | -11.22% | -13.52% | -8.976% | -6.758% | -13.01% | -13.51% | -7.113% | -9.136%
Emergency | 15.6513 | 15.5666 | 15.7496 | 15.9277 | 15.8194 | 15.7692 | 15.6858 | 16.3332 | 126.5027 | Emergency | -5.6471 | -5.2555 | -4.314 | -3.8889 | -3.3614 | -3.6784 | -3.4419 | -4.0926 | -33.6798 | Emergency | -36.08% | -33.76% | -27.39% | -24.42% | -21.25% | -23.33% | -21.94% | -25.06% | -26.62%
Repair | 13.7792 | 13.4796 | 13.2307 | 13.003 | 12.77 | 12.6599 | 12.3988 | 12.1743 | 103.4955 | Repair | -3.9725 | -3.6023 | -2.3314 | -1.5287 | -0.89614 | -1.136 | -0.72903 | -0.50766 | -14.7037 | Repair | -28.83% | -26.72% | -17.62% | -11.76% | -7.018% | -8.974% | -5.88% | -4.17% | -14.21%
Maintenance | 12.4076 | 12.5712 | 12.783 | 13.0432 | 12.8966 | 12.9205 | 12.7802 | 12.7958 | 102.1982 | Maintenance | 2.0289 | 5.2262 | 4.2294 | 4.5535 | 5.1061 | 4.7266 | 5.0152 | 4.9964 | 35.8823 | Maintenance | 16.35% | 41.57% | 33.09% | 34.91% | 39.59% | 36.58% | 39.24% | 39.05% | 35.11%
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Other Direct Activities | 8.5789 | 7.687 | 8.4026 | 8.7742 | 7.7786 | 8.1092 | 8.3306 | 8.1202 | 65.7813 | Other Direct Activities | 10.9341 | 6.0275 | 0.71223 | 1.259 | 1.7482 | 1.5463 | 1.3913 | 1.5401 | 25.1587 | Other Direct Activities | 127.5% | 78.41% | 8.476% | 14.35% | 22.47% | 19.07% | 16.7% | 18.97% | 38.25%
of which Xoserve | 5.0556 | 4.9045 | 5.5433 | 6.0774 | 4.9795 | 5.2697 | 5.4779 | 5.3102 | 42.6182 | of which Xoserve | -0.9268 | -0.66959 | -0.60744 | -0.67203 | -0.47073 | -0.78024 | -0.95441 | -0.86018 | -5.9414 | of which Xoserve | -18.33% | -13.65% | -10.96% | -11.06% | -9.453% | -14.81% | -17.42% | -16.2% | -13.94%
Total Direct Opex | 73.1069 | 72.1204 | 75.2175 | 74.4511 | 71.8903 | 73.2705 | 73.3278 | 71.5163 | 584.9008 | Total Direct Opex | 3.7991 | -0.16336 | -5.0908 | -1.7326 | 1.0676 | -1.6391 | -1.0254 | 0.36486 | -4.4198 | Total Direct Opex | 5.197% | -0.2265% | -6.768% | -2.327% | 1.485% | -2.237% | -1.398% | 0.5102% | -0.7556%
Business support | 22.6282 | 22.8026 | 23.0247 | 23.6735 | 23.7039 | 23.8621 | 23.9901 | 23.7609 | 187.446 | Business support | -6.2467 | -6.8587 | -6.4082 | -5.8167 | -4.877 | -4.2835 | -3.8857 | -3.0836 | -41.4601 | Business support | -27.61% | -30.08% | -27.83% | -24.57% | -20.57% | -17.95% | -16.2% | -12.98% | -22.12%
Training & Apprentices | 3.866 | 4.0414 | 4.3988 | 4.4343 | 4.6699 | 4.4977 | 4.5034 | 4.5406 | 34.9523 | Training & Apprentices | -1.9314 | -2.2519 | -2.2779 | -1.7133 | -1.1068 | -0.28939 | -0.19129 | -0.22294 | -9.9849 | Training & Apprentices | -49.96% | -55.72% | -51.79% | -38.64% | -23.7% | -6.434% | -4.248% | -4.91% | -28.57%
Total Indirect Opex | 26.4943 | 26.844 | 27.4235 | 28.1078 | 28.3739 | 28.3598 | 28.4935 | 28.3015 | 222.3982 | Total Indirect Opex | -8.1781 | -9.1106 | -8.6862 | -7.53 | -5.9838 | -4.5729 | -4.0769 | -3.3065 | -51.445 | Total Indirect Opex | -30.87% | -33.94% | -31.67% | -26.79% | -21.09% | -16.12% | -14.31% | -11.68% | -23.13%
Total Opex | 99.9567 | 99.3199 | 102.9964 | 102.9144 | 100.6197 | 101.9858 | 102.1768 | 100.1733 | 810.1429 | Total Opex | -4.7345 | -9.6294 | -14.1325 | -9.618 | -5.2716 | -6.5675 | -5.4578 | -3.2972 | -58.7085 | Total Opex | -4.737% | -9.695% | -13.72% | -9.346% | -5.239% | -6.44% | -5.342% | -3.291% | -7.247%
Total sub-deducts | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 5.6876 | Total sub-deducts | -0.71095 | -0.71095 | -0.41095 | -0.41095 | -0.41095 | -0.41095 | -0.41095 | -0.41095 | -5.6876 | Total sub-deducts | -100% | -100% | -57.8% | -57.8% | -57.8% | -57.8% | -57.8% | -57.8% | -100%
Total Controllable costs | 260.0886 | 255.1989 | 251.1081 | 247.712 | 246.4809 | 245.9568 | 249.3784 | 247.9681 | 2003.8918 | Total Controllable costs | -39.3592 | -44.7769 | -36.9416 | -34.8127 | -35.3226 | -36.3087 | -38.0455 | -38.8199 | -304.387 | Total Controllable costs | -15.13% | -17.55% | -14.71% | -14.05% | -14.33% | -14.76% | -15.26% | -15.66% | -15.19%
Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Non-Controllable costs | [9 empty] | Non-Controllable costs | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Licence/network/other | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 262.7254 | Licence/network/other | 7.4392 | 8.0145 | 5.4879 | 7.8879 | 7.8879 | 7.8879 | 7.8879 | 0.98791 | 53.4811 | Licence/network/other | 22.65% | 24.4% | 16.71% | 24.02% | 24.02% | 24.02% | 24.02% | 3.008% | 20.36%
NTS exit costs | 27.4099 | 27.4298 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 219.4264 | NTS exit costs | -6.2423 | -4.5019 | -7.8977 | -7.8977 | -7.8977 | -7.8977 | -7.8977 | -7.8977 | -58.1304 | NTS exit costs | -22.77% | -16.41% | -28.79% | -28.79% | -28.79% | -28.79% | -28.79% | -28.79% | -26.49%
Shrinkage | 10.5505 | 10.4063 | 10.3289 | 10.131 | 9.9805 | 9.8344 | 9.6864 | 9.3344 | 80.2524 | Shrinkage | -1.4654 | -3.646 | -4.6249 | -4.427 | -4.2765 | -4.1304 | -3.9824 | -3.6304 | -30.1829 | Shrinkage | -13.89% | -35.04% | -44.78% | -43.7% | -42.85% | -42% | -41.11% | -38.89% | -37.61%
NTS pensions contributions | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 37.5604 | NTS pensions contributions | -0.070394 | 0.0048439 | -0.023213 | -0.023213 | -0.023213 | -0.023213 | -0.023213 | -0.023213 | -0.20483 | NTS pensions contributions | -1.499% | 0.1032% | -0.4944% | -0.4944% | -0.4944% | -0.4944% | -0.4944% | -0.4944% | -0.5453%
Total non-controllable costs | 75.4962 | 75.3718 | 75.2957 | 75.0978 | 74.9473 | 74.8012 | 74.6532 | 74.3013 | 599.9646 | Total non-controllable costs | -0.33891 | -0.12864 | -7.0579 | -4.46 | -4.3095 | -4.1634 | -4.0154 | -10.5634 | -35.037 | Total non-controllable costs | -0.4489% | -0.1707% | -9.374% | -5.939% | -5.75% | -5.566% | -5.379% | -14.22% | -5.84%
Total funded costs - including agreed uncertainties** | 335.5848 | 330.5707 | 326.4038 | 322.8098 | 321.4283 | 320.758 | 324.0317 | 322.2693 | 2603.8564 | Total funded costs - including uncertainties | -39.6981 | -44.9055 | -43.9994 | -39.2727 | -39.6321 | -40.4721 | -42.0609 | -49.3833 | -339.424 | Total funded costs - including uncertainties | -11.83% | -13.58% | -13.48% | -12.17% | -12.33% | -12.62% | -12.98% | -15.32% | -13.04%
| 2.4896 | 5.6843e-14 | 0 | 0 | 5.6843e-14 | 0 | 0 | 0 | 2.4896 |  | -3.2048
Price conversion tables
Final proposals - £m | [9 empty] | Final proposals - £m
2009/10 prices | [9 empty] | 2014/15 prices
| Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
LTS, storage and entry | 13.8122 | 13.3101 | 11.9437 | 11.3966 | 12.7849 | 11.1309 | 10.3277 | 12.0673 | 96.7734 | LTS, storage and entry | 16.4304 | 15.8332 | 14.2077 | 13.5569 | 15.2084 | 13.2408 | 12.2854 | 14.3547 | 115.1174
Connections | 7.0994 | 7.2468 | 7.3383 | 7.5223 | 7.4347 | 7.6072 | 7.6604 | 7.7867 | 59.6959 | Connections | 8.4452 | 8.6205 | 8.7293 | 8.9482 | 8.844 | 9.0492 | 9.1125 | 9.2627 | 71.0116
Mains Reinforcement | 7.8261 | 7.8381 | 7.8485 | 7.8655 | 7.8755 | 7.8759 | 7.8783 | 7.9394 | 62.9473 | Mains Reinforcement | 9.3096 | 9.3239 | 9.3362 | 9.3565 | 9.3683 | 9.3688 | 9.3717 | 9.4443 | 74.8794
Governors (Replacement) | 2.2658 | 2.3665 | 2.1638 | 3.1428 | 2.8013 | 2.858 | 2.7021 | 3.1359 | 21.4362 | Governors (Replacement) | 2.6953 | 2.815 | 2.5739 | 3.7385 | 3.3323 | 3.3997 | 3.2144 | 3.7303 | 25.4995
Other Capex | 23.0261 | 21.8536 | 16.5438 | 13.6599 | 12.5456 | 12.4343 | 16.1117 | 15.5699 | 131.7448 | Other Capex | 27.3908 | 25.9961 | 19.6798 | 16.2492 | 14.9237 | 14.7913 | 19.1658 | 18.5212 | 156.7179
of which IT | 7.0366 | 6.7356 | 5.2485 | 4.9574 | 5.9858 | 5.6819 | 5.566 | 4.9857 | 46.1975 | of which IT | 8.3705 | 8.0123 | 6.2434 | 5.8971 | 7.1205 | 6.759 | 6.6211 | 5.9308 | 54.9546
of which Vehicles | 7.5877 | 6.0407 | 4.1958 | 3.7969 | 1.8756 | 2.1721 | 4.7346 | 4.527 | 34.9303 | of which Vehicles | 9.026 | 7.1858 | 4.9912 | 4.5166 | 2.2311 | 2.5838 | 5.632 | 5.3851 | 41.5516
Total Capex | 54.0297 | 52.6151 | 45.8381 | 43.5871 | 43.4421 | 41.9063 | 44.6803 | 46.499 | 372.5975 | Total Capex | 64.2713 | 62.5886 | 54.527 | 51.8494 | 51.6768 | 49.8499 | 53.1497 | 55.3132 | 443.2258
HSE driven mains & services | [8 empty] | 0 | HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Non-HSE driven mains & services | [8 empty] | 0 | Non-HSE driven mains & services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Multi occupancy buildings (MoBs) | [8 empty] | 0 | Multi occupancy buildings (MoBs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Repex | 78.4923 | 78.4246 | 78.6719 | 78.1369 | 79.1761 | 79.1229 | 79.0647 | 77.7446 | 628.834 | Total Repex | 93.371 | 93.2904 | 93.5847 | 92.9483 | 94.1844 | 94.1212 | 94.052 | 92.4816 | 748.0336
Work Management | 19.0744 | 19.1803 | 21.0595 | 19.9258 | 19.0203 | 20.0174 | 20.2868 | 18.5723 | 157.1369 | Work Management | 22.6901 | 22.8161 | 25.0515 | 23.7029 | 22.6257 | 23.8118 | 24.1323 | 22.0928 | 186.9232
Emergency | 13.1572 | 13.086 | 13.2399 | 13.3896 | 13.2986 | 13.2563 | 13.1863 | 13.7305 | 106.3444 | Emergency | 15.6513 | 15.5666 | 15.7496 | 15.9277 | 15.8194 | 15.7692 | 15.6858 | 16.3332 | 126.5027
Repair | 11.5835 | 11.3316 | 11.1224 | 10.931 | 10.7351 | 10.6425 | 10.4231 | 10.2343 | 87.0035 | Repair | 13.7792 | 13.4796 | 13.2307 | 13.003 | 12.77 | 12.6599 | 12.3988 | 12.1743 | 103.4955
Maintenance | 10.4304 | 10.568 | 10.746 | 10.9648 | 10.8416 | 10.8616 | 10.7437 | 10.7568 | 85.9128 | Maintenance | 12.4076 | 12.5712 | 12.783 | 13.0432 | 12.8966 | 12.9205 | 12.7802 | 12.7958 | 102.1982
Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Statutory independent undertakings (SIUs) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other Direct Activities | 7.2118 | 6.462 | 7.0637 | 7.376 | 6.5391 | 6.817 | 7.0031 | 6.8262 | 55.299 | Other Direct Activities | 8.5789 | 7.687 | 8.4026 | 8.7742 | 7.7786 | 8.1092 | 8.3306 | 8.1202 | 65.7813
of which Xoserve | 4.25 | 4.123 | 4.66 | 5.109 | 4.186 | 4.43 | 4.605 | 4.464 | 35.827 | of which Xoserve | 5.0556 | 4.9045 | 5.5433 | 6.0774 | 4.9795 | 5.2697 | 5.4779 | 5.3102 | 42.6182
Total Direct Opex | 61.4573 | 60.628 | 63.2315 | 62.5873 | 60.4346 | 61.5948 | 61.643 | 60.1201 | 491.6966 | Total Direct Opex | 73.1069 | 72.1204 | 75.2175 | 74.4511 | 71.8903 | 73.2705 | 73.3278 | 71.5163 | 584.9008
Business support | 19.0224 | 19.169 | 19.3557 | 19.9011 | 19.9267 | 20.0596 | 20.1673 | 19.9746 | 157.5763 | Business support | 22.6282 | 22.8026 | 23.0247 | 23.6735 | 23.7039 | 23.8621 | 23.9901 | 23.7609 | 187.446
Training & Apprentices | 3.25 | 3.3974 | 3.6979 | 3.7277 | 3.9258 | 3.781 | 3.7858 | 3.817 | 29.3826 | Training & Apprentices | 3.866 | 4.0414 | 4.3988 | 4.4343 | 4.6699 | 4.4977 | 4.5034 | 4.5406 | 34.9523
Total Indirect Opex | 22.2724 | 22.5664 | 23.0535 | 23.6288 | 23.8525 | 23.8407 | 23.9531 | 23.7916 | 186.959 | Total Indirect Opex | 26.4943 | 26.844 | 27.4235 | 28.1078 | 28.3739 | 28.3598 | 28.4935 | 28.3015 | 222.3982
Total Opex | 84.0285 | 83.4932 | 86.5839 | 86.5149 | 84.5859 | 85.7343 | 85.8949 | 84.2106 | 681.0462 | Total Opex | 99.9567 | 99.3199 | 102.9964 | 102.9144 | 100.6197 | 101.9858 | 102.1768 | 100.1733 | 810.1429
Total sub-deducts | 0.59766 | 0.59766 | 0.59766 | 0.59766 | 0.59766 | 0.59766 | 0.59766 | 0.59766 | 4.7813 | Total sub-deducts | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 0.71095 | 5.6876
Total Controllable costs | 216.5505 | 214.5328 | 211.0939 | 208.239 | 207.2041 | 206.7634 | 209.6399 | 208.4542 | 1682.4777 | Total Controllable costs | 257.599 | 255.1989 | 251.1081 | 247.712 | 246.4809 | 245.9568 | 249.3784 | 247.9681 | 2001.4022
Non-Controllable costs | [9 empty] | Non-Controllable costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Licence/network/other | 27.6075 | 27.6075 | 27.6075 | 27.6075 | 27.6075 | 27.6075 | 27.6075 | 27.6075 | 220.86 | Licence/network/other | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 32.8407 | 262.7254
NTS exit costs | 23.0421 | 23.0589 | 23.06 | 23.06 | 23.06 | 23.06 | 23.06 | 23.06 | 184.4607 | NTS exit costs | 27.4099 | 27.4298 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 27.4311 | 219.4264
Shrinkage | 8.8693 | 8.748 | 8.683 | 8.5166 | 8.3901 | 8.2673 | 8.1429 | 7.847 | 67.4642 | Shrinkage | 10.5505 | 10.4063 | 10.3289 | 10.131 | 9.9805 | 9.8344 | 9.6864 | 9.3344 | 80.2524
NTS pensions contributions | 3.9469 | 3.9469 | 3.9469 | 3.9469 | 3.9469 | 3.9469 | 3.9469 | 3.9469 | 31.5751 | NTS pensions contributions | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 4.695 | 37.5604
Total non-controllable costs | 63.4658 | 63.3613 | 63.2973 | 63.1309 | 63.0044 | 62.8816 | 62.7572 | 62.4613 | 504.3599 | Total non-controllable costs | 75.4962 | 75.3718 | 75.2957 | 75.0978 | 74.9473 | 74.8012 | 74.6532 | 74.3013 | 599.9646
Total funded costs | 280.0163 | 277.8941 | 274.3912 | 271.3699 | 270.2085 | 269.645 | 272.3971 | 270.9155 | 2186.8376 | Total funded costs | 333.0952 | 330.5707 | 326.4038 | 322.8098 | 321.4283 | 320.758 | 324.0317 | 322.2693 | 2601.3668
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Agreed Uncertainties** £m | [8 empty] | error | Agreed Uncertainties** £m
2014/15 prices
| Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Uncertainty | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Uncertainty | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Smart metering | [8 empty] | 0 | Smart metering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Streetworks | [8 empty] | 0 | Streetworks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PSUP | [8 empty] | 0 | PSUP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SIUs | [8 empty] | 0 | SIUs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other | [8 empty] | 0 | Other | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tier 2A adjustment | 2.4417 | [7 empty] | 2.4417 | Tier 2A adjustment | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896
[9 empty] | 0 | [9 empty] | 0
Total | 2.4417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4417 | Total | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896
Agreed uncertainties** by activity £m | [9 empty] | Agreed uncertainties** by activity £m
2014/15 prices
| Ofgem Allowance (Post IQI) £m | [9 empty] | Ofgem Allowance (Post IQI) £m
Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Controllable costs by activity | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
LTS, storage and entry | [8 empty] | 0 | LTS, storage and entry | [8 empty] | 0
Connections | [8 empty] | 0 | Connections | [8 empty] | 0
Mains Reinforcement | [8 empty] | 0 | Mains Reinforcement | [8 empty] | 0
Governors (Replacement) | [8 empty] | 0 | Governors (Replacement) | [8 empty] | 0
Other Capex | [8 empty] | 0 | Other Capex | [8 empty] | 0
of which IT | [8 empty] | 0 | of which IT | [8 empty] | 0
of which Vehicles | [8 empty] | 0 | of which Vehicles | [8 empty] | 0
Total Capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Capex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HSE driven mains & services | 2.4417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4417 | HSE driven mains & services | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896
Non-HSE driven mains & services | [8 empty] | 0 | Non-HSE driven mains & services | [8 empty] | 0
Multi occupancy buildings (MoBs) | [8 empty] | 0 | Multi occupancy buildings (MoBs) | [8 empty] | 0
Total Repex | 2.4417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4417 | Total Repex | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896
Work Management | [8 empty] | 0 | Work Management | [8 empty] | 0
Emergency | [8 empty] | 0 | Emergency | [8 empty] | 0
Repair | [8 empty] | 0 | Repair | [8 empty] | 0
Maintenance | [8 empty] | 0 | Maintenance | [8 empty] | 0
Statutory independent undertakings (SIUs) | [8 empty] | 0 | Statutory independent undertakings (SIUs) | [8 empty] | 0
Other Direct Activities | [8 empty] | 0 | Other Direct Activities | [8 empty] | 0
of which Xoserve | [8 empty] | 0 | of which Xoserve | [8 empty] | 0
Total Direct Opex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Direct Opex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Business support | [8 empty] | 0 | Business support | [8 empty] | 0
Training & Apprentices | [8 empty] | 0 | Training & Apprentices | [8 empty] | 0
Total Indirect Opex | [8 empty] | 0 | Total Indirect Opex | [8 empty] | 0
Total Opex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Total Opex | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total Controllable costs | 2.4417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4417 | Total Controllable costs | 2.4896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4896
| OK | OK | OK | OK | OK | OK | OK | OK | OK |  | OK | OK | OK | OK | OK | OK | OK | OK | OK
* These are uncertainties where a reopener has yet to be triggered and no decision on setting an allowance has been made. | [9 empty] | * These are uncertainties where a reopener has yet to be triggered and no decision on setting an allowance has been made.
** Agreed uncertainties are where a reopener has been triggered and a decision has been made by Ofgem. | [9 empty] | ** Agreed uncertainties are where a reopener has been triggered and a decision has been made by Ofgem.
Note on B97: Ruth Irvine: changed this to include all SM costs from table 3.14 - previously this line picked up only opex costs from table 3.1
Note on B98: Ruth Irvine: changed this to include all SWs costs from table 3.13 - previously this line picked up only opex costs from table 3.1

## Workload Summary
Regulatory Reporting Pack
Wales and West
2014/15
2.3 Summary of workload
Current year RRP submission 2015 - Workload
|  | Actuals | Forecast
Cost activity |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Opex
Mains condition reports | Number | 5636 | 6424 | 7421.4281 | 7428.6093 | 7422.7124 | 7402.5457 | 7366.8369 | 7314.2281 | 56416.3605
Service condition reports | Number | 6317 | 5417 | 5217.1751 | 5196.1094 | 5167.9255 | 5132.0256 | 5087.7722 | 5034.4861 | 42569.4938
No. of holders removed | Number | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 9
Capex
Total mains reinforcement | km | 11.3181 | 13.4404 | 9 | 10 | 10 | 10 | 10 | 10 | 83.7585
Total reinforcement Governors | Number | 0 | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 96
Total connection services | Number | 11498 | 11294 | 12947.75 | 12852 | 12866 | 12886 | 12886 | 12656 | 99885.75
- New housing services | Number | 2898 | 3595 | 2770.75 | 2826 | 2868 | 2868 | 2868 | 2868 | 23561.75
- Existing housing services | Number | 5381 | 5508 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 57689
- Non- domestic services | Number | 587 | 530 | 800 | 816 | 828 | 828 | 828 | 828 | 6045
- Fuel poor services | Number | 2632 | 1661 | 1577 | 1410 | 1370 | 1390 | 1390 | 1160 | 12590
Governor intervention | Number | 94 | 90 | 250 | 450.5 | 321 | 336.5 | 289.5 | 252 | 2083.5
Repex
T1 length decommissioned | km | 332.4631 | 365.6075 | 417.6 | 396.55 | 333.4 | 333.4 | 333.4 | 333.45 | 2845.8707
T2 length decommissioned | km | 21.6847 | 20.7114 | 29.7 | 29.7 | 29.7 | 29.7 | 29.7 | 29.775 | 220.6711
T3 length decommissioned | km | 1.371 | 1.7409 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.075 | 3.6869
Steel length decommissioned | km | 64.8401 | 66.7523 | 24.4 | 24.4 | 24.4 | 24.4 | 24.4 | 24.4 | 277.9925
Other length decommissioned | km | 29.407 | 26.1554 | 6.7 | 6.7 | 6.7 | 6.7 | 6.7 | 6.725 | 95.7874
No. of services transferred | Number | 19750 | 20361 | 23798.3591 | 23733.5835 | 20397.6094 | 20397.6094 | 20397.6094 | 20397.6094 | 169233.3802
No. of services relaid | Number | 22851 | 23770 | 25538.3847 | 25485.3865 | 22755.9532 | 22755.9532 | 22755.9532 | 22755.9532 | 188668.5838
Previous year RRP submission | [10 empty] | Variance from previous year | [10 empty] | % Variance from previous year
|  | Actuals 2014: Forecast | [5 empty] | Actuals | Forecast | [9 empty] | Actuals | Forecast
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 5636 | 7418.8337 | 7429.2112 | 7426.8036 | 7410.4389 | 7378.8661 | 7330.7495 | 7264.664 | 57295.567 | Mains condition reports | Number | 0 | -994.8337 | -7.7832 | 1.8058 | 12.2735 | 23.6796 | 36.0875 | 49.5641 | -879.2064 | Mains condition reports | Number | 0% | -13.41% | -0.1048% | 0.02431% | 0.1656% | 0.3209% | 0.4923% | 0.6823% | -1.535%
Service condition reports | Number | 6317 | 6547.0058 | 6527.6829 | 6501.3889 | 6467.5355 | 6425.4958 | 6374.6013 | 6314.1405 | 51474.8506 | Service condition reports | Number | 0 | -1130.0058 | -1310.5078 | -1305.2795 | -1299.61 | -1293.4702 | -1286.8292 | -1279.6544 | -8905.3568 | Service condition reports | Number | 0% | -17.26% | -20.08% | -20.08% | -20.09% | -20.13% | -20.19% | -20.27% | -17.3%
No. of holders removed | Number | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | No. of holders removed | Number | 0 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | No. of holders removed | Number | 0% | -12.5% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | -10%
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Capex |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Capex | [10 empty] | Capex
Total mains reinforcement | km | 11.3181 | 12 | 9 | 10 | 10 | 10 | 10 | 10 | 82.3181 | Total mains reinforcement | km | 0 | 1.4404 | 0 | 0 | 0 | 0 | 0 | 0 | 1.4404 | Total mains reinforcement | km | 0% | 12% | 0% | 0% | 0% | 0% | 0% | 0% | 1.75%
Total reinforcement Governors | Number | 0 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 112 | Total reinforcement Governors | Number | 0 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | -16 | Total reinforcement Governors | Number | #DIV/0! | -100% | 0% | 0% | 0% | 0% | 0% | 0% | -14.29%
Total connection services | Number | 11498 | 12928.33 | 12870.75 | 12867 | 12696 | 12696 | 12696 | 12696 | 100948.08 | Total connection services | Number | 0 | -1634.33 | 77 | -15 | 170 | 190 | 190 | -40 | -1062.33 | Total connection services | Number | 0% | -12.64% | 0.5983% | -0.1166% | 1.339% | 1.497% | 1.497% | -0.3151% | -1.052%
- New housing services | Number | 2898 | 2743.53 | 2770.75 | 2826 | 2868 | 2868 | 2868 | 2868 | 22710.28 | - New housing services | Number | 0 | 851.47 | 0 | 0 | 0 | 0 | 0 | 0 | 851.47 | - New housing services | Number | 0% | 31.04% | 0% | 0% | 0% | 0% | 0% | 0% | 3.749%
- Existing housing services | Number | 5381 | 7878 | 7800 | 7800 | 7800 | 7800 | 7800 | 7800 | 60059 | - Existing housing services | Number | 0 | -2370 | 0 | 0 | 0 | 0 | 0 | 0 | -2370 | - Existing housing services | Number | 0% | -30.08% | 0% | 0% | 0% | 0% | 0% | 0% | -3.946%
- Non- domestic services | Number | 587 | 791.8 | 800 | 816 | 828 | 828 | 828 | 828 | 6306.8 | - Non- domestic services | Number | 0 | -261.8 | 0 | 0 | 0 | 0 | 0 | 0 | -261.8 | - Non- domestic services | Number | 0% | -33.06% | 0% | 0% | 0% | 0% | 0% | 0% | -4.151%
- Fuel poor services | Number | 2632 | 1515 | 1500 | 1425 | 1200 | 1200 | 1200 | 1200 | 11872 | - Fuel poor services | Number | 0 | 146 | 77 | -15 | 170 | 190 | 190 | -40 | 718 | - Fuel poor services | Number | 0% | 9.637% | 5.133% | -1.053% | 14.17% | 15.83% | 15.83% | -3.333% | 6.048%
Governor intervention | Number | 94 | 219.25 | 250 | 450.5 | 321 | 336.5 | 289.5 | 252 | 2212.75 | Governor intervention | Number | 0 | -129.25 | 0 | 0 | 0 | 0 | 0 | 0 | -129.25 | Governor intervention | Number | 0% | -58.95% | 0% | 0% | 0% | 0% | 0% | 0% | -5.841%
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repex |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Repex | [10 empty] | Repex
T1 length decommissioned | km | 332.4631 | 329.7 | 329.7 | 329.7 | 329.7 | 329.7 | 329.7 | 329.7 | 2640.3631 | T1 length decommissioned | km | 0 | 35.9075 | 87.9 | 66.85 | 3.7 | 3.7 | 3.7 | 3.75 | 205.5075 | T1 length decommissioned | km | 0% | 10.89% | 26.66% | 20.28% | 1.122% | 1.122% | 1.122% | 1.137% | 7.783%
T2 length decommissioned | km | 21.6847 | 29.7 | 29.7114 | 29.7454 | 29.7454 | 29.7454 | 29.7454 | 29.7481 | 229.8258 | T2 length decommissioned | km | 0 | -8.9886 | -0.011353 | -0.045414 | -0.045414 | -0.045414 | -0.045414 | 0.026915 | -9.1547 | T2 length decommissioned | km | 0% | -30.26% | -0.03821% | -0.1527% | -0.1527% | -0.1527% | -0.1527% | 0.09048% | -3.983%
T3 length decommissioned | km | 1.371 | 0.1 | 0.10004 | 0.10015 | 0.10015 | 0.10015 | 0.10015 | 0.10016 | 2.0718 | T3 length decommissioned | km | 0 | 1.6409 | -3.8227e-05 | -0.00015291 | -0.00015291 | -0.00015291 | -0.00015291 | -0.025162 | 1.6151 | T3 length decommissioned | km | 0% | 1641% | -0.03821% | -0.1527% | -0.1527% | -0.1527% | -0.1527% | -25.12% | 77.96%
Steel length decommissioned | km | 64.8401 | 56.4 | 71.4093 | 71.4373 | 71.4373 | 71.4373 | 71.4373 | 71.4395 | 549.8382 | Steel length decommissioned | km | 0 | 10.3523 | -47.0093 | -47.0373 | -47.0373 | -47.0373 | -47.0373 | -47.0395 | -271.8457 | Steel length decommissioned | km | 0% | 18.36% | -65.83% | -65.84% | -65.84% | -65.84% | -65.84% | -65.85% | -49.44%
Other length decommissioned | km | 29.407 | 6.7 | 6.7026 | 6.7102 | 6.7102 | 6.7102 | 6.7102 | 6.7108 | 76.3614 | Other length decommissioned | km | 0 | 19.4554 | -0.0025612 | -0.010245 | -0.010245 | -0.010245 | -0.010245 | 0.014153 | 19.426 | Other length decommissioned | km | 0% | 290.4% | -0.03821% | -0.1527% | -0.1527% | -0.1527% | -0.1527% | 0.2109% | 25.44%
No. of services transferred | Number | 19750 | 23749.7774 | 22948.1716 | 20397.6094 | 20397.6094 | 20397.6094 | 20397.6094 | 20397.6094 | 168435.9961 | No. of services transferred | Number | 0 | -3388.7774 | 850.1874 | 3335.9741 | 0 | 0 | 0 | 0 | 797.3841 | No. of services transferred | Number | 0% | -14.27% | 3.705% | 16.35% | 0% | 0% | 0% | 0% | 0.4734%
No. of services relaid | Number | 22851 | 19431.636 | 18775.7768 | 16688.9532 | 16688.9532 | 16688.9532 | 16688.9532 | 16688.9532 | 144503.1786 | No. of services relaid | Number | 0 | 4338.364 | 6762.6079 | 8796.4333 | 6067 | 6067 | 6067 | 6067 | 44165.4052 | No. of services relaid | Number | 0% | 22.33% | 36.02% | 52.71% | 36.35% | 36.35% | 36.35% | 36.35% | 30.56%
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final proposals | [10 empty] | Variance from final proposals | [10 empty] | % Variance from final proposals
[13 empty] | Actuals |  |  | Forecast | [7 empty] | Actuals |  |  | Forecast
Workload
Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total | Cost activity | Units | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Opex | [10 empty] | Opex | [10 empty] | Opex
Mains condition reports | Number | 9724.5789 | 9495.3985 | 9271.956 | 9054.1448 | 8841.8599 | 8634.9981 | 8433.4609 | 8237.1539 | 71693.5508 | Mains condition reports | Number | -4088.5789 | -3071.3985 | -1850.5279 | -1625.5354 | -1419.1475 | -1232.4524 | -1066.624 | -922.9258 | -15277.1903 | Mains condition reports | Number | -42.04% | -32.35% | -19.96% | -17.95% | -16.05% | -14.27% | -12.65% | -11.2% | -21.31%
Service condition reports | Number | 5054.1887 | 4985.2576 | 4901.9519 | 4801.158 | 4680.8179 | 4540.6366 | 4372.7139 | 4180.8059 | 37517.5306 | Service condition reports | Number | 1262.8113 | 431.7424 | 315.2231 | 394.9513 | 487.1076 | 591.389 | 715.0582 | 853.6803 | 5051.9632 | Service condition reports | Number | 24.99% | 8.66% | 6.431% | 8.226% | 10.41% | 13.02% | 16.35% | 20.42% | 13.47%
No. of holders removed | Number | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 0-1 | c. 7-8 | No. of holders removed | Number | [9 empty] | No. of holders removed | Number | [8 empty] | #VALUE!
Capex | [10 empty] | Capex | [10 empty] | Capex
Total mains reinforcement | km | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 200 | Total mains reinforcement | km | -13.6819 | -11.5596 | -16 | -15 | -15 | -15 | -15 | -15 | -116.2415 | Total mains reinforcement | km | -54.73% | -46.24% | -64% | -60% | -60% | -60% | -60% | -60% | -58.12%
Total reinforcement Governors | Number | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 128 | Total reinforcement Governors | Number | -16 | -16 | 0 | 0 | 0 | 0 | 0 | 0 | -32 | Total reinforcement Governors | Number | -100% | -100% | 0% | 0% | 0% | 0% | 0% | 0% | -25%
Total connection services | Number | 12165 | 12230 | 12305 | 12365 | 12140 | 12215 | 12285 | 12355 | 98060 | Total connection services | Number | -667 | -936 | 642.75 | 487 | 726 | 671 | 601 | 301 | 1825.75 | Total connection services | Number | -5.483% | -7.653% | 5.223% | 3.939% | 5.98% | 5.493% | 4.892% | 2.436% | 1.862%
- New housing services | Number | 2485 | 2535 | 2590 | 2640 | 2690 | 2750 | 2805 | 2860 | 21355 | - New housing services | Number | 413 | 1060 | 180.75 | 186 | 178 | 118 | 63 | 8 | 2206.75 | - New housing services | Number | 16.62% | 41.81% | 6.979% | 7.045% | 6.617% | 4.291% | 2.246% | 0.2797% | 10.33%
- Existing housing services | Number | 7465 | 7465 | 7465 | 7465 | 7475 | 7475 | 7475 | 7475 | 59760 | - Existing housing services | Number | -2084 | -1957 | 335 | 335 | 325 | 325 | 325 | 325 | -2071 | - Existing housing services | Number | -27.92% | -26.22% | 4.488% | 4.488% | 4.348% | 4.348% | 4.348% | 4.348% | -3.466%
- Non- domestic services | Number | 715 | 730 | 750 | 760 | 775 | 790 | 805 | 820 | 6145 | - Non- domestic services | Number | -128 | -200 | 50 | 56 | 53 | 38 | 23 | 8 | -100 | - Non- domestic services | Number | -17.9% | -27.4% | 6.667% | 7.368% | 6.839% | 4.81% | 2.857% | 0.9756% | -1.627%
- Fuel poor services | Number | 1500 | 1500 | 1500 | 1500 | 1200 | 1200 | 1200 | 1200 | 10800 | - Fuel poor services | Number | 1132 | 161 | 77 | -90 | 170 | 190 | 190 | -40 | 1790 | - Fuel poor services | Number | 75.47% | 10.73% | 5.133% | -6% | 14.17% | 15.83% | 15.83% | -3.333% | 16.57%
Governor intervention | Number | 42 | 53 | 56 | 61 | 66 | 74 | 77 | 85 | 514 | Governor intervention | Number | 52 | 37 | 194 | 389.5 | 255 | 262.5 | 212.5 | 167 | 1569.5 | Governor intervention | Number | 123.8% | 69.81% | 346.4% | 638.5% | 386.4% | 354.7% | 276% | 196.5% | 305.4%
Repex | [10 empty] | Repex | [10 empty] | Repex
T1 length decommissioned | km | 331.5076 | 330.961 | 330.434 | 329.9258 | 329.4358 | 328.9635 | 328.5083 | 328.0695 | 2637.8056 | T1 length decommissioned | km | 0.9555 | 34.6465 | 87.166 | 66.6242 | 3.9642 | 4.4365 | 4.8917 | 5.3805 | 208.0651 | T1 length decommissioned | km | 0.2882% | 10.47% | 26.38% | 20.19% | 1.203% | 1.349% | 1.489% | 1.64% | 7.888%
T2 length decommissioned | km | 30.1528 | 29.8319 | 28.3167 | 28.2533 | 32.3017 | 30.904 | 28.6746 | 28.7351 | 237.1702 | T2 length decommissioned | km | -8.4681 | -9.1205 | 1.3833 | 1.4467 | -2.6017 | -1.204 | 1.0254 | 1.0399 | -16.4991 | T2 length decommissioned | km | -28.08% | -30.57% | 4.885% | 5.12% | -8.054% | -3.896% | 3.576% | 3.619% | -6.957%
T3 length decommissioned | km | 0.12355 | 0.12355 | 0.12355 | 0.12355 | 0.12355 | 0.12355 | 0.12355 | 0.12355 | 0.98842 | T3 length decommissioned | km | 1.2474 | 1.6173 | -0.023552 | -0.023552 | -0.023552 | -0.023553 | -0.023553 | -0.048553 | 2.6985 | T3 length decommissioned | km | 1010% | 1309% | -19.06% | -19.06% | -19.06% | -19.06% | -19.06% | -39.3% | 273%
Steel length decommissioned | km | 71.6237 | 71.5443 | 71.4675 | 71.3934 | 71.3219 | 71.2528 | 71.186 | 71.1215 | 570.9112 | Steel length decommissioned | km | -6.7836 | -4.792 | -47.0675 | -46.9934 | -46.9219 | -46.8528 | -46.786 | -46.7215 | -292.9187 | Steel length decommissioned | km | -9.471% | -6.698% | -65.86% | -65.82% | -65.79% | -65.76% | -65.72% | -65.69% | -51.31%
Other length decommissioned | km | 7.2313 | 7.1443 | 6.9943 | 7.0123 | 6.8163 | 6.7863 | 6.8003 | 6.8573 | 55.6422 | Other length decommissioned | km | 22.1757 | 19.0112 | -0.29427 | -0.31228 | -0.11628 | -0.086283 | -0.10029 | -0.13229 | 40.1452 | Other length decommissioned | km | 306.7% | 266.1% | -4.207% | -4.453% | -1.706% | -1.271% | -1.475% | -1.929% | 72.15%
No. of services transferred | Number | 16553.6787 | 16530.0223 | 16538.733 | 16501.034 | 16536.0676 | 16476.732 | 16474.1113 | 16492.1039 | 132102.4827 | No. of services transferred | Number | 3196.3213 | 3830.9777 | 7259.6261 | 7232.5494 | 3861.5418 | 3920.8775 | 3923.4981 | 3905.5055 | 37130.8975 | No. of services transferred | Number | 19.31% | 23.18% | 43.89% | 43.83% | 23.35% | 23.8% | 23.82% | 23.68% | 28.11%
No. of services relaid | Number | 26440.2014 | 26524.1324 | 26653.347 | 26651.5127 | 26389.4372 | 26092.5755 | 25806.4502 | 25771.7966 | 210329.453 | No. of services relaid | Number | -3589.2014 | -2754.1324 | -1114.9623 | -1166.1262 | -3633.484 | -3336.6223 | -3050.497 | -3015.8435 | -21660.8692 | No. of services relaid | Number | -13.57% | -10.38% | -4.183% | -4.375% | -13.77% | -12.79% | -11.82% | -11.7% | -10.3%
|  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Safety Outputs
Regulatory Reporting Pack
Wales and West
2014/15
2.4 Summary of safety outputs and secondary deliverables
Actual/forecast iron mains risk reduction (incidents/year x 10-6) - Primary output
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 197562.9 | 172591.9 | 148530.9 | 130068.0264 | 116719.7423 | 109164.2237 | 102439.2237 | 96252.2237
Mains risk reduction | 24971 | 24061 | 18462.8736 | 13348.2841 | 7555.5186 | 6725 | 6187 | 5360
Main risk c/f | 172591.9 | 148530.9 | 130068.0264 | 116719.7423 | 109164.2237 | 102439.2237 | 96252.2237 | 90892.2237
Cumulative mains risk reduction | 24971 | 49032 | 67494.8736 | 80843.1577 | 88398.6763 | 95123.6763 | 101310.6763 | 106670.6763
Previous year forecast iron mains risk reduction (incidents/year x 10-6) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals | Forecast | [7 empty] | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Mains risk b/f | 197562.9 | 172591.9 | 151982.9 | 134088.9 | 120390.9 | 110494.9 | 104153.9 | 100993.9
Mains risk reduction | 24971 | 20609 | 17894 | 13698 | 9896 | 6341 | 3160 | 2160 | Mains risk reduction | 0 | 3452 | 568.8736 | -349.7159 | -2340.4814 | 384 | 3027 | 3200 | Mains risk reduction | 0% | 16.75% | 3.179% | -2.553% | -23.65% | 6.056% | 95.79% | 148.1%
Main risk c/f | 172591.9 | 151982.9 | 134088.9 | 120390.9 | 110494.9 | 104153.9 | 100993.9 | 98833.9
Cumulative mains risk reduction | 24971 | 45580 | 63474 | 77172 | 87068 | 93409 | 96569 | 98729 | Cumulative mains risk reduction | 0 | 3452 | 4020.8736 | 3671.1577 | 1330.6763 | 1714.6763 | 4741.6763 | 7941.6763 | Cumulative mains risk reduction | 0% | 7.573% | 6.335% | 4.757% | 1.528% | 1.836% | 4.91% | 8.044%
Final proposals allowed iron mains risk reduction for RIIO-GD1 (incidents/year x 10-6) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Mains risk reduction | 98727 | [7 empty] | Mains risk reduction | 7943.6763 | [7 empty] | Mains risk reduction | -100%
Actual/forecast repair risk
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Repair risk 2013 (start position) | 24.2
Annual repair risk | 24.6862 | 18.6322 | 24.18 | 24.18 | 24.18 | 24.18 | 24.18 | 24.18
Movement in risk | -0.48624 | 5.5678 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
Previous year's forecast repair risK | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals | Forecast | [7 empty] | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Annual repair risk | 24.6862 | 25.5977 | 25.5796 | 25.5215 | 25.4198 | 25.2707 | 25.0702 | 24.814 | Annual repair risk | 0 | -6.9655 | -1.3996 | -1.3415 | -1.2398 | -1.0907 | -0.89021 | -0.63395 | Repair risk reduction | 0% | -27.21% | -5.471% | -5.256% | -4.877% | -4.316% | -3.551% | -2.555%
Movement in risk | -24.6862 | -25.5977 | -25.5796 | -25.5215 | -25.4198 | -25.2707 | -25.0702 | -24.814 | Movement in risk | 24.2 | 31.1655 | 25.5996 | 25.5415 | 25.4398 | 25.2907 | 25.0902 | 24.834
Safety - Emergency response - Primary output
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Total PREs | 90885 | 87141
(1) Controllable
Number of controlled gas escapes or controlled other gas emergencies reported | 33617 | 32066
Number of responses within timescale (2 hours) | 33444 | 31938
Percentage of controlled gas escapes responded to within timescale (2 hours) | 99.49% | 99.6%
(2) Non-controllable
Number of uncontrolled gas escapes or uncontrolled other gas emergencies reported | 57268 | 55075
Number of responses within timescale (1 hour) | 56314 | 54236
Percentage of uncontrolled gas escapes responded to within timescale (1 hour) | 98.33% | 98.48%
Proportion of gas escapes prevented within 12 hrs (secondary deliverable) | 46.65% | 49.47%
Gas in Buildings (GIB) events - Iron mains - Secondary deliverable
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
GIB events reportable under RIDDOR ie GIB >= 20% LEL or > 10kg from spun/cast iron fracture or DI corrosion of mains of: | 1 | 3 | 2 | 2 | 2 | 2 | 2 | 2
GIB events (any % level) from spun/cast iron fracture or DI corrosion of mains of: | 37 | 45
Cast/spun iron fractures and ductile iron corrosion failures - Secondary deliverable
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Number of spun/cast iron fracture or DI corrosion of mains of: | 581 | 616 | 1066 | 1066 | 1066 | 1066 | 1066 | 1066
Sub-deduct networks - secondary deliverable
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
% off sub-deduct networks taken of risk | 8.28% | 9.554% | 70% | 90% | 100% | 0% | 0% | 0%
| 8.28% | 17.83% | 87.83% | 177.8% | 277.8% | 277.8% | 277.8% | 277.8%
Note on A71: Ofgem: Any concentration level at any location in the building. Data to include all GIB instances including those reportable under RIDDOR

## Reliability Outputs
Regulatory Reporting Pack
Wales and West
2014/15
2.5 Summary of reliability outputs and secondary deliverables
Summary of loss of supply volumes and duration - primary output
Actual/forecast loss of supply volumes (no.)
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 53085 | 55623 | 57490 | 57490 | 48285 | 47679 | 47679 | 47676 | 415007
No. of unplanned interruptions | 9478 | 10062 | 10315 | 10064 | 9883 | 9689 | 9474 | 9238 | 78203
Total interruptions | 62563 | 65685 | 67805 | 67554 | 58168 | 57368 | 57153 | 56914 | 493210
Previous year forecast loss of supply volumes (no.) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals | Forecast | [8 empty] | Actuals | Forecast | [8 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 53085 | 55545 | 56383 | 56142 | 55643 | 55800 | 55899 | 56015 | 444512 | No. of planned interruptions | 0 | 78 | 1107 | 1348 | -7358 | -8121 | -8220 | -8339 | -29505 | No. of planned interruptions | 0% | 0.1404% | 1.963% | 2.401% | -13.22% | -14.55% | -14.71% | -14.89% | -6.638%
No. of unplanned interruptions | 9478 | 10803.9 | 11045.4 | 11287 | 11527.7 | 11768.3 | 12009 | 12249.6 | 90168.9 | No. of unplanned interruptions | 0 | -741.9 | -730.4 | -1223 | -1644.7 | -2079.3 | -2535 | -3011.6 | -11965.9 | No. of unplanned interruptions | 0% | -6.867% | -6.613% | -10.84% | -14.27% | -17.67% | -21.11% | -24.59% | -13.27%
Total interruptions | 62563 | 66348.9 | 67428.4 | 67429 | 67170.7 | 67568.3 | 67908 | 68264.6 | 534680.9 | Total interruptions | 0 | -663.9 | 376.6 | 125 | -9002.7 | -10200.3 | -10755 | -11350.6 | -41470.9 | Total interruptions | 0% | -1.001% | 0.5585% | 0.1854% | -13.4% | -15.1% | -15.84% | -16.63% | -7.756%
Final proposals allowed loss of supply volumes (no.) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
No. of planned interruptions | 451235.3356 | [8 empty] | No. of planned interruptions | -36228.3356 | [8 empty] | No. of planned interruptions | -8.029%
No. of unplanned interruptions | 90169.2225 | [8 empty] | No. of unplanned interruptions | -11966.2225 | [8 empty] | No. of unplanned interruptions | -13.27%
Total interruptions | 541404.558 | [8 empty] | Total interruptions | -48194.558 | [8 empty] | Total interruptions | -8.902%
Actual/forecast loss of supply duration (mins - million of)
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 13.0837 | 13.6775 | 13.2743 | 12.4119 | 9.9417 | 9.817 | 9.817 | 9.8163 | 91.8395
No. of unplanned interruptions | 6.1219 | 9.4034 | 4.9636 | 4.8428 | 4.7557 | 4.6623 | 4.5589 | 4.4453 | 43.754
Total interruptions | 19.2057 | 23.081 | 18.2378 | 17.2547 | 14.6974 | 14.4793 | 14.3759 | 14.2617 | 135.5935
Previous year forecast loss of supply duration (mins - million of) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals | Forecast | [8 empty] | Actuals | Forecast | [8 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
No. of planned interruptions | 13.0837 | 11.2 | 11.4 | 11.3 | 11.2 | 11.3 | 11.3 | 11.3 | 92.0837 | No. of planned interruptions | 0 | 2.4775 | 1.8743 | 1.1119 | -1.2583 | -1.483 | -1.483 | -1.4837 | -0.24426 | No. of planned interruptions | 0% | 22.12% | 16.44% | 9.84% | -11.23% | -13.12% | -13.12% | -13.13% | -0.2653%
No. of unplanned interruptions | 6.1219 | 5.7465 | 5.875 | 6.0035 | 6.1315 | 6.2595 | 6.3875 | 6.5155 | 49.0409 | No. of unplanned interruptions | 0 | 3.6569 | -0.91142 | -1.1607 | -1.3758 | -1.5972 | -1.8286 | -2.0702 | -5.2869 | No. of unplanned interruptions | 0% | 63.64% | -15.51% | -19.33% | -22.44% | -25.52% | -28.63% | -31.77% | -10.78%
Total interruptions | 19.2057 | 16.9465 | 17.275 | 17.3035 | 17.3315 | 17.5595 | 17.6875 | 17.8155 | 141.1247 | Total interruptions | 0 | 6.1345 | 0.96285 | -0.048781 | -2.6341 | -3.0802 | -3.3116 | -3.5538 | -5.5312 | Total interruptions | 0% | 36.2% | 5.574% | -0.2819% | -15.2% | -17.54% | -18.72% | -19.95% | -3.919%
Final proposals allowed loss of supply duration (mins - million of) | [9 empty] | Variance from final proposals | [9 empty] | Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
No. of planned interruptions | 92.052 | [8 empty] | No. of planned interruptions | -0.21251 | [8 empty] | No. of planned interruptions | -0.2309%
No. of unplanned interruptions | 45.0846 | [8 empty] | No. of unplanned interruptions | -1.3306 | [8 empty] | No. of unplanned interruptions | -2.951%
Total interruptions | 137.1366 | [8 empty] | Total interruptions | -1.5431 | [8 empty] | Total interruptions | -1.125%
Summary of telemetered faults - secondary deliverables
Actual/forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs))
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 15.8 | 5.23 | 78 | 78 | 78 | 78 | 78 | 78 | 489.03
Previous year forecast telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals | Forecast | [8 empty] | Actuals | Forecast | [8 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
Telemetered faults | 15.8 | 78 | 78 | 78 | 78 | 78 | 78 | 78 | 561.8 | Telemetered faults | 0 | -72.77 | 0 | 0 | 0 | 0 | 0 | 0 | -72.77 | Telemetered faults | 0% | -93.29% | 0% | 0% | 0% | 0% | 0% | 0% | -12.95%
Final proposals allowed telemetered faults (fault * duration/no. of telemetered AGIs - "now faults" (hrs)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
Telemetered faults | 181 | 168 | 153 | 141 | 161 | 182 | 202 | 223 | 1411 | Telemetered faults | -165.2 | -162.77 | -75 | -63 | -83 | -104 | -124 | -145 | -921.97 | Telemetered faults | -91.27% | -96.89% | -49.02% | -44.68% | -51.55% | -57.14% | -61.39% | -65.02% | -65.34%
Summary of pressure systems safety regulations (PSSR) faults - secondary deliverables
Actual/forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate))
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 48.1% | 5.7% | 7.1% | 7% | 7.2% | 7.4% | 7.6% | 7.8%
Previous year forecast PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from previous year | [9 empty] | % Variance from previous year
| Actuals | Forecast | [8 empty] | Actuals | Forecast | [8 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | Forecast RIIO Total
PSSR faults (% or No.) | 48.1% | 47.4% | 46.8% | 46.1% | 47.4% | 48.8% | 50.1% | 51.4% |  | PSSR faults (% or No.) | 0 | -0.417 | -0.397 | -0.391 | -0.402 | -0.414 | -0.425 | -0.436 |  | PSSR faults (% or No.) | 0% | -87.97% | -84.83% | -84.82% | -84.81% | -84.84% | -84.83% | -84.82%
Final proposals allowed PSSR faults (faults as a % of inspections - PSSR A1 and A2 faults or faults/No. of AGIs - PSSR A1 and A2 faults (delete as appropriate)) | [9 empty] | Variance from final proposals | [9 empty] | % Variance from final proposals
| Final proposals | [9 empty] | Final proposals | [9 empty] | Final proposals
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | RIIO Total
PSSR faults (% or No.) | 7.3% | 7.2% | 7.1% | 7% | 7.2% | 7.4% | 7.6% | 7.8% | 58.6% | PSSR faults (% or No.) | 0.408 | -0.015 | 0 | 0 | 0 | 0 | 0 | 0 |  | PSSR faults (% or No.) | 558.9% | -20.83% | 0% | 0% | 0% | 0% | 0% | 0%
Number and value of offtake meter error reports
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Volume of offtake meter errors (GWh) | 11.716 | 16.542 | 65.482 | 65.344 | 65.461 | 65.72 | 66.025 | 65.94
Throughput (GWh) | 62420 | 59865 | 65482 | 65344 | 65461 | 65720 | 66025 | 65940
Meter errors/throughput (%) | 0.01877% | 0.02763% | 0.1% | 0.1% | 0.1% | 0.1% | 0.1% | 0.1%
Summary Capacity Utilisation
Capacity utilisation | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
</= 50% | 171 | 164 | 164 | 164 | 164 | 164 | 164 | 164
>50% to </=70% | 81 | 80 | 80 | 80 | 80 | 80 | 80 | 80
>70% to </=80% | 39 | 39 | 39 | 39 | 39 | 39 | 39 | 39
>80% to </=100% | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 51
>100% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total no. of sites | 342 | 334 | 334 | 334 | 334 | 334 | 334 | 334

## Environmental Outputs
Regulatory Reporting Pack
Wales and West
2014/15
2.6 Summary of environmental outputs - shrinkage and leakage volumes
Actual/forecast shrinkage volumes (GWh)
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 421.185
Shrinkage volume | 421.185 | 394.7673 | 396.629 | 388.1724 | 381.7181 | 375.3756 | 368.9832 | 362.4046
Shrinkage volume reduction | 0 | 26.4177 | 24.556 | 33.0127 | 39.4669 | 45.8094 | 52.2018 | 58.7805
% shrinkage volume reduction | 0% | 6.272% | 5.83% | 7.838% | 9.37% | 10.88% | 12.39% | 13.96%
Previous year forecast shrinkage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals | Forecast | [7 empty] | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Shrinkage volumes at start of RIIO-GD1 | 421.185
Shrinkage volume | 421.185 | 413.6222 | 405.3309 | 397.5245 | 389.6304 | 381.8735 | 373.8241 | 365.7847 | Shrinkage volume | 0 | -18.8548 | -8.7019 | -9.3521 | -7.9123 | -6.4979 | -4.8409 | -3.3802 | Shrinkage volume | 0% | -4.558% | -2.147% | -2.353% | -2.031% | -1.702% | -1.295% | -0.9241%
Shrinkage volume reduction | 0 | 7.5629 | 15.8542 | 23.6606 | 31.5546 | 39.3115 | 47.3609 | 55.4003 | Shrinkage volume reduction | 0 | 18.8548 | 8.7019 | 9.3521 | 7.9123 | 6.4979 | 4.8409 | 3.3802 | Shrinkage volume reduction | #DIV/0! | 249.3% | 54.89% | 39.53% | 25.07% | 16.53% | 10.22% | 6.101%
Final proposals allowed shrinkage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Shrinkage volume reduction | 14% | [7 empty] | Shrinkage volume reduction | -0.18543 | [7 empty] | Shrinkage volume reduction | -0.04403%
Actual/forecast leakage volumes (GWh)
| Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 401.8348
Leakage volume | 401.8348 | 376.0295 | 376.1331 | 367.7197 | 361.2288 | 354.8052 | 348.3174 | 341.7653
Leakage volume reduction | 0 | 25.8053 | 25.7016 | 34.1151 | 40.6059 | 47.0295 | 53.5174 | 60.0694
% Leakage volume reduction | 0% | 6.422% | 6.396% | 8.49% | 10.11% | 11.7% | 13.32% | 14.95%
Previous year forecast leakage volumes (GWh) | [8 empty] | Variance from previous year | [8 empty] | % Variance from previous year
| Actuals | Forecast | [7 empty] | Actuals | Forecast | [7 empty] | Actuals | Forecast
| 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 |  | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021
Leakage volumes at start of RIIO-GD1 | 401.8348
Leakage volume | 401.8348 | 392.7048 | 384.6874 | 376.9911 | 369.2178 | 361.3667 | 353.4372 | 345.4283 | Leakage volume | 0 | -16.6753 | -8.5543 | -9.2714 | -7.989 | -6.5615 | -5.1198 | -3.663 | Leakage volume | 0% | -4.246% | -2.224% | -2.459% | -2.164% | -1.816% | -1.449% | -1.06%
Leakage volume reduction | 0 | 9.13 | 17.1473 | 24.8437 | 32.617 | 40.468 | 48.3976 | 56.4064 | Leakage volume reduction | 0 | 16.6753 | 8.5543 | 9.2714 | 7.989 | 6.5615 | 5.1198 | 3.663 | Leakage volume reduction | #DIV/0! | 182.6% | 49.89% | 37.32% | 24.49% | 16.21% | 10.58% | 6.494%
Final proposals allowed leakage volumes (GWh) | [8 empty] | Variance from final proposals | [8 empty] | % Variance from final proposals
| Final proposals | [8 empty] | Final proposals | [8 empty] | Final proposals
Leakage volume reduction | 14.7% | [7 empty] | Leakage volume reduction | 0.99971 | [7 empty] | Leakage volume reduction | 0.2488%

## Guaranteed Standards
Regulatory Reporting Pack
Wales and West
2014/15
8.3 Guaranteed Standards of Service
Guaranteed Standard 1 - Regulation 7 - Supply Restoration
Domestic
Number of customers' premises not restored within the prescribed period (Reg 7(2)(a)) | 1758
Number of customers' premises not restored within the prescribed period (Reg 7(2)(b)) | 1022
Number of payments made under Reg 7(2)(a) | 1758
Value of payments made under Reg 7(2)(a) | 52740
Number of payments made under Reg 7(2)(b) | 3010
Value of payments made under Reg 7(2)(b) | 90300
Number of times cap reached for payments under Reg 7(2) | 0
Total value of domestic payments made under Regulation 7 | 143040
Non Domestic
Number of customers' premises not restored within the prescribed period (Reg 7(2)(a)) | 38
Number of customers' premises not restored within the prescribed period (Reg 7(2)(b)) | 16
Number of payments made under Reg 7(2)(a) | 38
Value of payments made under Reg 7(2)(a) | 1900
Number of payments made under Reg 7(2)(b) | 46
Value of payments made under Reg 7(2)(b) | 2300
Number of times cap reached for payments under Reg 7(2) | 0
Total value of non-domestic payments made under Regulation 7 | 4200
Total value of domestic and non-domestic payments made under Regulation 7 | 147240
Guaranteed Standard 2 - Regulation 8 - Reinstatement of customer's premises
Domestic
Number of customers' premises due to be reinstated | 12377
Number of customers' premises not reinstated within the prescribed period (Reg 8(2)(a)) | 275
Number of customers' premises not reinstated within the prescribed period (Reg 8(2)(b)) | 49
Number of payments made under Reg 8(2)(a) | 275
Value of payments made under Reg 8(2)(a) | 13750
Number of payments made under Reg 8(2)(b) | 135
Value of payments made under Reg 8(2)(b) | 6750
Total value of payments made under Regulation 8 to domestic customers | 20500
Non Domestic
Number of customers' premises due to be reinstated | 326
Number of customers' premises not reinstated within the prescribed period (Reg 8(2)(a)) | 6
Number of customers' premises not reinstated within the prescribed period (Reg 8(2)(b)) | 2
Number of payments made under Reg 8(2)(a) | 6
Value of payments made under Reg 8(2)(a) | 600
Number of payments made under Reg 8(2)(b) | 4
Value of payments made under Reg 8(2)(b) | 400
Total value of payments made under Regulation 8 to non-domestic customers | 1000
Total value of payments made under Regulation 8 | 21500
Guaranteed Standard 3 - Regulation 9 - Priority domestic customers
Number of supply interruptions to priority domestic customers' premises (Reg 9(1)) | 6960.384
Planned interruptions
Number of planned interruptions to priority domestic customers' premises (Reg 9(2)(a)) | 5896.038
Number of payments made under Reg 9(2)(a) | 17
Value of payments made under Reg 9(2)(a) | 408
Unplanned interruptions (less than 250 premises)
Number of unplanned interruptions to priority domestic customers' premises where less than 250 customers' premises are affected (Reg 9(2)(b)(i)) | 950.184
Number of payments made under Reg 9(2)(b)(i) | 2
Value of payments made under Reg 9(2)(b)(i) | 48
Unplanned interruptions (more than 250 premises)
Number of unplanned interruptions to priority domestic customers' premises where 250 or more customers' premises are affected (Reg 9(2)(b)(ii)) | 114.162
Number of payments made under Reg 9(2)(b)(ii) | 12
Value of payments made under Reg 9(2)(b)(ii) | 288
Total value of payments made under Regulation 9 | 744
Guaranteed Standard 4 - Regulation 10 - Provision of standard connection quotations =<275kWh per hour
Voluntary Scheme
Number of requests for standard quote =<275kWh per hour (Reg 10(1)(a)) | 4824 | 1822
Number of standard quotations provided within prescribed period (Reg 10 (3) (a)) | 4803 | 1815
Number of standard quotations not provided within prescribed period (Reg 10(3)(a)) | 21 | 7
Number of payments made under Reg 10(3)(a) | 146 | 41
Number of times cap reached for payments under Reg 10(6)(b)(i) | 1 | 1
Value of payments made under Regulation 10(3)(a) | 1460 | 410
Exclusions
Number of excluded connections | 2495
Number of complex connections | 0
Number of connections where customer failed to provide required information | 0
Number of customer requested deferrals | 0
Number of connections not covered by SI (connections >7 bar gauge, domestic developments and non-domestic developments) | 0
Guaranteed Standard 5 - Regulation 10 - Provision of non-standard connection quotations =<275kWh per hour
Voluntary Scheme
Number of requests for non-standard quote =<275kWh per hour (Reg 10(1)(a)) | 5586 | 2462
Number of non-standard quotations provided within prescribed period (Reg 10(3)(b)(i)) | 5514 | 2420
Number of non-standard quotations not provided within prescribed period (Reg 10(3)(b)(i)) | 72 | 42
Number of payments made under Reg 10(3)(b)(i) | 457 | 258
Number of times cap reached for payments under Reg 10(6)(b)(i) | 6 | 2
Value of payments made under Regulation 10(3)(b)(i) | 4570 | 2580
Exclusions
Number of excluded connections | 346
Number of complex connections | 0
Number of connections where customer failed to provide required information | 0
Number of customer requested deferrals | 0
Number of connections not covered by SI (connections >7 bar gauge, domestic developments and non-domestic developments) | 9
Guaranteed Standard 6 - Regulation 10 - Provision of non-standard connection quotations > 275kWh per hour
Voluntary Scheme
Number of requests for non-standard quote >275kWh per hour (Reg 10(1)(a)) | 69 | 419
Number of non-standard quotations provided within prescribed period (Reg 10(3)(b)(ii)) | 67 | 410
Number of non-standard quotations not provided within prescribed period (Reg 10(3)(b)(ii)) | 2 | 9
Number of payments made under Reg 10(3)(b)(ii) | 2 | 62
Number of times cap reached for payments under Reg 10(6)(b)(ii) | 0 | 2
Value of payments made under Regulation 10 (3)(b)(ii) | 40 | 1240
Exclusions
Number of excluded connections | 1359
Number of complex connections | 40
Number of connections where customer failed to provide required information | 0
Number of customer requested deferrals | 0
Number of connections not covered by SI (connections >7 bar gauge, domestic developments and non-domestic developments) | 324
Guaranteed Standard 7 - Regulation 10 - Accuracy of quotations
Voluntary Scheme
Number of quotations challenged under accuracy scheme (Reg 10(1)(b)) | 0 | 0
Number of quotations found not to be accurate (Reg 10(3)(c)) | 0 | 0
Number of refunds issued following accuracy scheme challenge | 0 | 0
Value of refunds issued under accuracy scheme (Reg 10 (3)(c)) | 0 | 0
Exclusions
Number of excluded connections | 0
Number of complex connections | 0
Number of connections where customer failed to provide required information | 0
Number of customer requested deferrals | 0
Number of connections not covered by SI (connections >7 bar gauge, domestic developments and non-domestic developments) | 0
Guaranteed Standard 8 - Regulation 10 - Response to land enquiries
Voluntary Scheme
Number of land enquiry requests received (Reg 10(1)(c)) | 3 | 446
Number of land enquiry requests responded to within timescale (Reg 10(3)(d)) | 3 | 444
Number of land enquiry requests not responded to within timescale (Reg 10(3)(d)) | 0 | 2
Number of payments made under Reg 10(3)(d) | 0 | 2
Number of times cap reached for payments under Reg 10(6)(c)(i)(ii) | 0 | 1
Value of payments made under Regulation 10(3)(d) | 0 | 540
Exclusions
Number of excluded connections | 539
Number of complex connections | 0
Number of connections where customer failed to provide required information | 0
Number of customer requested deferrals | 0
Number of connections not covered by SI (connections >7 bar gauge, domestic developments and non-domestic developments) | 539
Guaranteed Standard 9 - Regulation 10 - Offering a date for commencement and substantial completion of connection works (=<275kWh per hour)
Voluntary
Number of quotations accepted (Reg 10(1)(d)) | 6570 | 2396
Number where both dates offered within timescale (Reg 10(3)(e)(i)) | 6565 | 2393
Number where at least one date not offered within timescale (Reg 10(3)(e)(i)) | 5 | 3
Number of payments made under Reg 10(3)(e)(i) | 45.5 | 20.5
Number of times cap reached for payments under Reg 10(6)(d)(i) | 3 | 1
Value of payments made under Regulation 10(3)(e)(i) | 910 | 410
Guaranteed Standard 10 - Regulation 10 - Offering a date for commencement and substantial completion of connection works (> 275kWh per hour)
Voluntary Scheme
Number of quotations accepted (Reg 10(1)(d)) | 27 | 145
Number where both dates offered within timescale (Reg 10(3)(e)(ii)) | 26 | 145
Number where at least one date not offered within timescale (Reg 10(3)(e)(ii)) | 1 | 0
Number of payments made under Reg 10(3)(e)(ii) | 5 | 0
Number of times cap reached for payments under Reg 10(6)(d)(ii) | 0 | 0
Value of payments made under Regulation 10(3)(e)(ii) | 200 | 0
Guaranteed Standard 11 - Regulation 10 - Substantial completion on agreed date
Quotation value up to and including £1,000 |  | Voluntary Scheme
Number substantially completed within timescale agreed with customer (Reg 10(3)(f)(i)) | 5402 | 1748
Number not substantially completed within timescale agreed with customer (Reg 10(3)(f)(i)) | 341 | 81
Number of payments made under Reg 10(3)(f)(i) | 1012 | 303
Number of times cap reached for payments under Reg 10(6)(e) | 46 | 17
Value of payments made under Regulation 10(3)(f)(i) | 20240 | 6060
Quotation value over £1,000 but not exceeding £4,000 |  | Voluntary Scheme
Number substantially completed within timescale agreed with customer (Reg 10(3)(f)(ii)) | 558 | 492
Number not substantially completed within timescale agreed with customer (Reg 10(3)(f)(ii)) | 62 | 44
Number of payments made under Reg 10(3)(f)(ii) | 191 | 184
Number of times cap reached for payments under Reg 10(6)(f) | 6 | 9
Value of payments made under Regulation 10(3)(f)(ii) | 9103.7255 | 9876.872
Quotation value over £4,000 but not exceeding £20,000 |  | Voluntary Scheme
Number substantially completed within timescale agreed with customer (Reg 10(3)(f)(iii)) | 60 | 114
Number not substantially completed within timescale agreed with customer (Reg 10(3)(f)(iii)) | 8 | 6
Number of payments made under Reg 10(3)(f)(iii) | 48 | 33.1813
Number of times cap reached for payments under Reg 10(6)(f) | 0 | 1
Value of payments made under Regulation 10(3)(f)(iii) | 4800 | 3318.1325
Quotation value above £20,000 but not exceeding £50,000 |  | Voluntary Scheme
Number substantially completed within timescale agreed with customer (Reg 10(3)(f)(iv)) | 1 | 9
Number not substantially completed within timescale agreed with customer (Reg 10(3)(f)(iv)) | 0 | 1
Number of payments made under Reg 10(3)(f)(iv) | 0 | 8
Number of times cap reached for payments under Reg 10(6)(g) | 0 | 0
Value of payments made under Regulation 10(3)(f)(iv) | 0 | 800
Quotation value above £50,000 but not exceeding £100,000 |  | Voluntary Scheme
Number substantially completed within timescale agreed with customer (Reg 10)(3)(f)(v)) | 0 | 4
Number not substantially completed within timescale agreed with customer (Reg 10(3)(f)(v) | 0 | 0
Number of payments made under Reg 10(3)(f)(v) | 0 | 0
Number of times cap reached for payments under Reg 10(6)(h) | 0 | 0
Value of payments made under Regulation 10(3)(f)(v) | 0 | 0
Total Amount |  | Voluntary Scheme
Total number of substantially completed quotations | 6432 | 2499
Total number substantially completed within agreed timescale | 6021 | 2367
Total number not substantially completed within agreed timescale (Reg 10(3)(f) | 411 | 132
Total number of payments made (Reg 10(3)(f)) | 1251 | 528.1813
Total number of times cap reached for payments (Reg 10(6)(e) - (h)) | 52 | 27
Total value of payments made (Regulation 10(3)(f)) | 34143.7255 | 20055.0045
Guaranteed Standard 13 - Regulation 10A - Notification of planned supply interruptions
Domestic
Number of customers whose gas supply was interrupted for planned maintenance or replacement work | 39328
Number of customers that did not receive prior notice of not less than prescribed period (Reg 10A(2)) | 619
Number of payments made under Reg 10A(2) | 15
Value of payments made under Reg 10A(2) | 300
Non Domestic
Number of customers whose gas supply was interrupted for planned maintenance or replacement work | 415
Number of customers that did not receive prior notice of not less than prescribed period (Reg 10A(2)) | 32
Number of payments made under Reg 10A(2) | 0
Value of payments made under Reg 10A(2) | 0
Total value of payments made under Reg 10A | 300
Guaranteed Standard 14 - Regulation 10B - Response to complaints
Total number of written and oral complaints received requiring a response | 2900
Number of customers that did not receive a response within the prescribed period (Reg 10B(2)) | 3
Number of payments made under Reg 10B(2) | 3
Number of times cap reached for payments under Reg 10B(4)(e) | 0
Total value of payments made under Reg 10B | 60
Guaranteed Standard 12 - Regulation 12 - Payments
Domestic
Number of payments due under Reg 12 | 23
Value of payments made under Regulation 12 to domestic customers | 460
Non Domestic
Number of payments due under Reg 12 | 0
Value of payments made under Regulation 12 to non-domestic customers | 0
Value of payments made under Reg 12 | 460
Voluntary Scheme
Total value of payments made under the Guaranteed Standards | 211627.7255 | 25235.0045

## Licence Condition D10
Regulatory Reporting Pack
Wales and West
2014/15
8.4 Licence Condition D10
Standard Special Condition D10(2)(a) Provision of standard connection quotations =<275 kWh per hour
Annual
Number of requests for standard quotation =<275kWh per hour (Standard Special Condition D10 (1)(a)) | 6646
Number of standard quotations provided within timescale (Standard Special Condition D10 (2)(a)) | 6618
Percentage of standard quotations provided within timescale (Standard Special Condition D10 (2)(a)) | 99.58%
Number of standard quotations not provided within timescale (Standard Special Condition D10 (2)(a) | 28
Percentage of standard quotations not provided within timescale (Standard Special Condition D10 (2)(a)) | 0.4213%
Standard Special Condition D10(2)(b)(i) Provision of non-standard connection quotations =<275kWh per hour
Annual
Number of requests for non-standard quotation =<275kWh per hour (Standard Special Condition D10 (1)(a)) | 8048
Number of non-standard quotations provided within timescale (Standard Special Condition D10 (2)(b)(i)) | 7934
Percentage of non-standard quotations provided within timescale (Standard Special Condition D10 (2)(b)(i)) | 98.58%
Number of non-standard quotations not provided within timescale (Standard Special Condition D10 (2)(b)(i)) | 114
Percentage of non-standard quotations not provided within timescale (Standard Special Condition D10 (2)(b)(i)) | 1.417%
Standard Special Condition D10(2)(b)(ii) Provision of non-standard connections quotations >275kWh per hour
Annual
Number of requests for non-standard quotation >275kWh per hour (Standard Special Condition D10 (1)(a)) | 488
Number of non-standard quotations provided within timescale (Standard Special Condition D10 (2)(b)(ii)) | 477
Percentage of non-standard quotations provided within timescale (Standard Special Condition D10 (2)(b)(ii)) | 97.75%
Number of non-standard quotations not provided within timescale (Standard Special Condition D10 (2)(b)(ii)) | 11
Percentage of non-standard quotations not provided within timescale (Standard Special Condition D10 (2)(b)(ii)) | 2.254%
Standard Special Condition D10(3) Accuracy of quotations
Annual
Number of quotations challenged under accuracy scheme (Standard Special Condition D10 (3) | 0
Number of quotations found not to be accurate (Standard Special Condition D10 (3)) | 0
Number of refunds issued following accuracy scheme challenge (Standard Special Condition D10 (3)) | 0
Total value of refunds issued following accuracy scheme challenge (Standard Special Condition D10 (3)) | 0
Standard Special Condition D10(2)(d) Response to land enquiries
Annual
Number of land enquiry requests received (Standard Special Condition D10 (1)(c)) | 449
Number of land enquiry requests responded to within timescale (Standard Special Condition D10 (2)(d)) | 447
Percentage of land enquiry requests responded to within timescale (Standard Special Condition D10 (2)(d)) | 99.55%
Number of land enquiry requests not responded to within timescale (Standard Special Condition D10 (2)(d)) | 2
Percentage of land enquiry requests not responded to within timescale (Standard Special Condition D10 (2)(d)) | 0.4454%
Standard Special Condition D10(2)(e) Provision of a date for commencement and substantial completion
Annual
Number of quotations accepted | 9138
Number where both dates offered within timescale (Standard Special Condition D10 (2)(e)) | 9129
Percentage where both dates provided within timescale (Standard Special Condition D10 (2)(e)) | 99.9%
Number where at least one date not offered within timescale (Standard Special Condition D10 (2)(e)) | 9
Percentage where at least one date not offered within timescale (Standard Special Condition D10 (2)(e)) | 0.09849%
Standard Special Condition D10(2)(c) Substantial completion of works within timescales agreed with the customer.
Annual
Total number of projects completed | 8931
Number substantially completed within timescale agreed with customer (Standard Special Condition D10 (2)(c)) | 8388
Percentage substantially completed within timescale agreed with customer (Standard Special Condition D10 (2)(c)) | 93.92%
Number not substantially completed within timescale agreed with customer (Standard Special Condition D10 (2)(c)) | 543
Percentage not substantially completed within timescale agreed with customer (Standard Special Condition D10 (2)(c)) | 6.08%
Standard Special Condition D10(2)(f) Responding to telephone calls
Annual
Total calls received on specified numbers | 2178239
Total calls answered within timescale | 2024947
Percentage of telephone calls answered within timescale | 92.96%