## Guidance on the document
This document is the 'Action Plan' element of our Digitalisation Strategy & Action Plan. It should be reviewed in conjunction with our published strategy. The commitments in this plan link back to the strategy document for ease of reading
The strategy will be updated every 2 years as a minimum with a 6 monthly update of progress against the plan and any additions
The plan includes a Gantt Chart for ease of use. Planned or in progress tasks are in blue, completed are green and tasks at risk of delivery on target are in amber for transparency
In addition to the colour coding of the Gantt chart, we also include text to inform readers of progress. There will be a column of text for every 6 month period for ease of tracking progress over time
Additional tasks added through our ongoing stakeholder engagament will be highlighted as 'new' in the relevant period update
We welcome any feedback, good or bad to inform and shape future versions of our strategy and plan
Any queries or feedback can be directed to Ian.Dunstan@wwutilities.co.uk

## The WWU Plan
|  |  | 2021 | [11 empty] | 2022 | [11 empty] | 2023
Commitment | Key deliverables | Current status | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Ongoing consultation on strategy and plan | Publish strategy and inform stakeholders | Completed | bar: 2021 Jan; 2022 Mar; 2022 Dec
| Digitalisation specific engagement events | A number of engagement events are planned to inform the next strategy update | bar: 2021 Jul to 2021 Sep; 2022 Jul to 2022 Sep; 2023 Feb
| Receive and review feedback | We are in constant touch with stakeholders on their data needs. There are a number of new lines added to the plan as a result of stakeholder feedback to date
| Use of Pathfinder Lite by additional parties (tbc) | Under review - legal licences under draft - Been trialled under 'Tools of Engagement phase 2' NIA project with 8 external bodies including some Local Authorities | bar: 2021 Aug to 2023 Dec
| Monthly review of data requests received via ENA data triage process | Ongoing but feeding into data sharing plan
| Constoer Engagement Groups and Citizens Panels - programme of engagement | A programme of engagement focused on or CEG and a number of citizens panels we operate | bar: 2023 Feb to 2023 Jul
2. Upgrade our core asset repository and finance systems | Complete future system design | Complete | bar: 2021 Jan to 2021 Feb
| Build phase of new system | Build is underway with a large team of IT and Business experts supporting. We are currently reviewing complexity to ensure delivery risk is minimised whilst still delivering the improvements and ambitions of ourselves and our stakeholders
| Data migration - cleansing and preparing data for new asset structures | Over 1million records have been reviewed and many thousands improved in readiness for data migration | bar: 2021 Jan to 2022 Sep
| Cutover to new system | April 2021 saw the launch of our new Customer Experience (CX) system. This is already helping us to serve our customers more effectively and efficiently than ever before.September saw the launch of our HR system. Next phase, we are prioritising changes to our Emergency & Repair systems and processes with the introduction of a new smart App for Operational colleagues. Changes will be accompanied by the roll out of new iPad’s, replacing outdated CF19 devices | bar: 2021 May to 2023 Dec
3. Digitise remaining asset data sets | Complete Service Governor surveys and digitisation programme | Physical surveys complete but impacted by covid. Currently updating our GIS system and asset repository. New app built to improve survey process for future condition surveys. HSE have reviewed app with positive feedback | bar: 2021 Jan to 2022 Jun
| Cathodic Protection Systems digitised and mapped to assets | HP system in Wales digitised and currently collecting data from Operational colleagues in the South West | bar: 2021 Apr to 2022 Jun; 2023 Jul to 2023 Dec
| Multi-Occupancy Building (MOBs) moved from standalone databases to core asset repository | High rise data prepared awaiting migration process to new SAP | bar: 2021 Jan to 2022 Jun; 2023 Jul to 2023 Dec
4. Internet of Things (IoT) | Innovation project on trial sites to explore sensors, remote monitoring and remote maintenance technologies | ICS Project completed with ICS consultancy using existing data to flag gaps that could be filled by sensor technology. Considering a phase II project on 2 PRI sites | bar: 2021 Apr to 2021 Dec
| NIA projects to explore sensor technology on PRIs - focus on emissions | Project scoped and going to national workshop in Februsry | bar: 2021 Apr to 2021 Dec
| Delivery of remote pressure control at test sites as part of project Optinet | Complete | bar: 2021 Jan to 2021 May; 2023 Feb to 2023 Aug
| Develop a strategy and plan for sensors and monitoring | Virtual team of operational; Asset And IT people assesmbled | bar: 2021 Sep to 2022 Apr
| Deliver phase 1 of the IoT plan | Not started | bar: 2022 May to 2022 Dec
| DPLA SIF project | Sit on steering committee and focused on phase 2 sign off | bar: 2022 Sep to 2023 Apr
| Derive GD3 IoT plan | Early workshops held | bar: 2022 Oct to 2023 Dec
5. Publish a metadata catalogue | Derive 1st catalogue based on stakeholder themes | A catalogue of data and publications has been developed and we are currently designing version 2 | bar: 2021 Jan to 2021 Mar
| Publish on our website and inform stakeholders | Complete | bar: 2021 Apr
| 6 monthly review and update to metadata catalogue | Under review | bar: 2021 Oct to 2021 Nov; 2022 Apr to 2022 May; 2022 Oct to 2022 Nov
| Project to procure metadata tool and populate | In plan for IT re-opener | bar: 2023 Apr to 2023 Dec
6. Pathfinder | Use of Pathfinder in a number of projects including:
| Milford Haven Energy Kingdom - Innovate UK project | Project in final stages of completion | bar: 2021 Jan to 2022 May
| EPIC - West of England Combined Authority (tbc) | Project in progress. Currently supporting data provision for whole system CBA use | bar: 2021 Feb to 2022 Dec
| Zero 2050 - South Wales Decarbonisation planning | Complete | bar: 2021 Jan to 2021 Mar
| Zero 2050 - South Wales Decarbonisation roll out to the rest of Wales (TBC) | Plan under review - replaced by a Welsh Government Project which we are supporting - details yet to be made public
| Gas Goes Green workstream 1.3 local, regional & mational pathways studies | Complete | bar: 2021 Jan to 2021 Oct
| Develop a Business Parks version of Pathfinder | A collaborative project with Blaena Gwent Local Authority | bar: 2021 Oct to 2022 Apr
| Appoint LAEP engagement team | LAEP manager appointed with role to support LAEps and WS CBAs with Las. 2 supporting roles in recruitment process | bar: 2023 Jan to 2023 Dec
| Engage on further projects and use cases | Updates are detailed as new lines at the bottom of this page
7. Priority Services Register (PSR) | Productionalise PSR data on maps to help plan projects | Concept proved but not productionalised following legal advice on GDPR | bar: 2021 Jan to 2021 Jul
| Resolve GDPR issues over use of PSR data in maps | Not able to overcome GDPR issues | bar: 2021 Apr to 2021 Oct
| Innovation project to add ONS and licenced data on demographics to further support planning | Reviewed Warm Wales (Fresh) data. Sample sets taken. Currently developing use cases using available demographic data | bar: 2021 Apr to 2022 Apr
| Build analytic tools to use the data and drive communciation plans and target projects and campaigns | ARCGIS reviewed - new improved mapping data contract to improves ease of data access to 3rd parties. Currently trialling internally with operational colleagues
8. National map | Actively participate in ENA subgroup PoC | POC complete and project report written. Currently deciding on next steps | bar: 2021 Jan to 2021 Dec
| Develop system to seemlessly publish data to the national map | We have easy access to GIS data through use of a new GIS system | bar: 2021 Oct to 2022 Mar
| Productionalise national map and increase data sets available | Not started. Will be driven by learning from the PoC | bar: 2022 Apr to 2022 Dec
9. Create a dedicated data and analytics team | GD2 Business restructure | Complete | bar: 2021 Jan to 2021 Mar
| Populate data and analytics team | Team built but some members are involved in our SAP upgrade and won't join the team until year end. Analytics offering under development | bar: 2021 Apr to 2021 Sep
| Implement new data triage process | Process through ENA adopted within WWU. We have a representative on the ENA data trige subgroup reviewing success and managing future improvements | bar: 2021 Jul to 2021 Sep
| Publish methods for external stakeholders to engage | Done via ENA currently | bar: 2021 Oct
10. Sharing future data sets | Gas goes green - green gas data reporting through ENA | Proposals discussed with GGG Advisory Group | bar: 2021 Jun; 2021 Dec; 2022 Jun; 2022 Nov
| Publish detailed environmental performance data | This is now published annually tough RRP | bar: 2021 Jun to 2021 Aug; 2022 Jun to 2022 Aug
| Publish heat and hot water ready reckoner | This is complete | bar: 2021 Apr to 2021 May
New: Whole System CBA tool | Promote and support use of Whole System Cost Benefit Analysis tool developed as part of Open Network | This is a new line item added in this period. One of our team co-led the project to create the tool. Currently suppoting various innoavtion projects and other use cases | bar: 2021 Jun to 2023 Dec
New: Flexible Generation Forecaster | Flexible Generation Forecaster for real time developed as part of a WWU led innovation project: https://www.smarternetworks.org/project/nia_wwu_068 | This is a new line item added in this period. This is now complete | bar: 2021 Jan to 2021 May
| Agree mechanism to share Flexble Generation Forecaster wth project partners | Complete | bar: 2021 Jun to 2021 Jul
| Share Flexible Generation Forecaster with non-funding parties (tbc) | Shared with parties including SGN and Cadent | bar: 2021 Jul to 2022 Dec
New: Pathfinder Lite | Development of Pathfinder Lite as part of Innovate UK Project: Bank Energi | Complete | bar: 2021 Jan to 2021 May
| Agree mechanism to share Pathfinder Lite | Under review - legal licences under draft | bar: 2021 Jun to 2021 Jul
| Use of Pathfinder Lite by additional parties (tbc) | Under review - legal licences under draft - Been trialled under 'Tools of Engagement phase 2' NIA project with 8 external bodies including some Local Authorities | bar: 2021 Aug to 2022 Dec
NUAR | National Underground Asset Register (NUAR) is now coming to Wales. This is a plant protection tool that gives a one stop shop plant protection service | We have signed a data sharing agreement and have shared sample data for the team to explore. We hope to move to a live system in 2022 | bar: 2021 Dec to 2022 Dec
| Metadata agreed and approved | Worked with NUAR team | bar: 2022 Jul to 2022 Dec
| Share WWU data | We have set up our GIS system to export data as required | bar: 2022 Jul to 2022 Dec
| Continued participation in NUAR development | Ongoing but attending all project meetings and a small user group created within WWU | bar: 2022 Dec to 2023 Dec
Data sharing and triage | Purchase and deliver a data sharing platform | Will be part of IT re-opener | bar: 2023 Jul to 2023 Dec
| Launch of website | Ongoing process - main site gone live with data page under development | bar: 2022 Nov to 2023 Mar
| Metadata catalogue system | Will be part of IT re-opener | bar: 2023 Jul to 2023 Dec
| Suite of metadata expanded | Will be part of IT re-opener | bar: 2023 Jul to 2023 Dec
| Recruitment of Data Governance and Data Digitlalisation manager | Job descriptions written and paper with Exec for approval | bar: 2023 Feb to 2023 May
| AGOl and GIS launch | Ssystem built and UAT in progress | bar: 2023 Apr to 2023 Jul
Startegic infrastructure Staregy Group
| Data shared using Data Map Wales Platform | Data on future work published and overlaying with LA work | bar: 2022 Aug to 2023 Jan
| Engaged LAs, other utilities and Welsh government on data sharing | Working closely with Welsh Government, LAs and othe utilities and transport organisations | bar: 2022 Apr to 2023 Dec
System transformation programme | Analysts appointed | bar: 2022 May to 2022 Aug
| BEI/ARUP data licences agreed for system transformation programme | NDA written and in final sign-off process | bar: 2022 Jun to 2023 Mar
| 10% of network analysed for hydrogen transformation | Analysed Gloucester region with the output being work needed and associated cost to tranform the region to hydrogen | bar: 2022 Jun to 2022 Dec
Programme to transform System Control systems scoped and to be delievred | bar: 2022 Jul to 2023 Dec
| PSTN process | Contract signed with supplier, trial sites completed and programme commenced | bar: 2022 Apr to 2023 Dec
| Cost of conversion programme completed | High level cost of investment in assets to make hydrogen ready | bar: 2022 Jan to 2022 Jul