## Guidance on the document
This document is the 'Action Plan' element of our Digitalisation Strategy & Action Plan. It should be reviewed in conjunction with our published strategy. The commitments in this plan link back to the strategy document for ease of reading.
The strategy will be updated every 2 years as a minimum with a 6 monthly update of progress against the plan and any additions.
The plan includes a Gantt Chart for ease of use. Planned or in progress tasks are in blue, completed are green and tasks at risk of delivery on target are in amber for transparency.
In addition to the colour coding of the Gantt chart, we also include text to inform readers of progress.
Additional tasks added through our ongoing stakeholder engagament will be highlighted as 'new' in the relevant period update.
We are committed providing stakeholders with the opportunity to share their opinions on our strategy, action plan, projects and initiatives. Any feedback and suggestions will be gratefully received and can be sent to the mailbox engagement@wwutilities.co.uk Specific enquiries requesting data or about open or previously shared data should be directed to data.requests@wwutilities.co.uk.

## The WWU Plan
We identify our stakeholders’ wants, needs, perspectives and behaviours through appropriate engagement activities analysing and reviewing feedback alongside our own and external insight to inform business decision-making and shape the delivery of the services that matter to all our stakeholders. |  |  |  | delivery behind schedule | [6 empty] | delivery on track | [6 empty] | delivery complete
Digitalisation Strategy Framework Alignment | Key Deliverable(s) | Target Benefit to Stakeholdes | Current Status | 2024 | [5 empty] | 2025 | [11 empty] | 2026
|  |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar
Products & Services | Pathfinder | • Improved accuracy due to revised cost data (updated based on cost of living increases), additional energy demand options (e.g. H2 cars/HGVs), and live data feeds where possible • Enhanced capabilities enabling Pathfinder to run multiple scenarios simultaneously • Improved access and shareability via online-hosted platform with more user-friendly outputs | Completed minor updates and improvements to the existing Product. In 2026, we plan to develop a tool to create an online version to improve accessibility for local authorities in the region to enable them to better design their own energy systems. A possible dependency on NESO could impact this plan and its provisional timeline. | 2025 Feb: Updates to existing product; 2026 Jan: Plan to develop tool to create online version of Pathfinder
| Priority Services Register (PSR) | Enable us to provide the tailered support our customers need and to share those needs with other utilities and support organisations | During RIIO-GD2, we committed to referring 12,000 new customers to the Gas Industry PSR per year. We are on track to meet or exceed this target with over 15,000 referred in 2024/25, bringing us to a total of over 46,000 referrals at the end of year 4. There are now 27% of domestic homes in our network registered on the Gas Suppliers PSR, up from 22% at the start of RIIO-GD2. We share our sign-ups with the relevant Distribution Network Operator (electricity). They in turn share with water and the energy suppliers thereby avoiding duplication. | 2024 Jul: Exceeded 12-month target, referring 15,000 new customers to the Gas Industry PSR; 2025 Apr: Ongoing collaboration with the utilities sector to promote the benefits of being on the Priority Service Register. Ongoing active sign-up and referral of new customers to meet annual target and support creation of a virtual single utilities PSR register
| Digitise remaining asset data sets | Improved asset risk data ensuring investment is targeted and 'just in time'. This avoids over investment on assets | Multi occupancy building and strategic valve location and condition surveys are in progress with data being digitised in the back office. To be completed by end RIIO-GD2. | 2024 Jul: Ongoing physical surveys to support digitisation of outstanding assets (e.g. MOB, Pipeline Isolation Valves (PIV), etc.); 2025 Jun: RRP Reporting; 2025 Jul: Further physical surveys and refinement of data sets
| Open Data Sharing | Publishing data to help the wider UK make decisions on net zero and supporting consumers through the journey | Completed Proof of Concept in Microsoft Fabric using demand data. Data catalogue being developed as part of data governance activities in People & Processes workstream. Bi-weekly attendance at Gas Data & Digitalisation Collaboration Group to support development of interoperable data set for asset data. | 2025 Feb: Proof of Concept; 2025 May: Ongoing engagement with Gas Data & Digitalisation Collaboration Group around interoperability and asset data sharing. Open Data Platform planned for 2026 go-live (see Technology project below)
| Blending suite | Tools that will support hydrogen producers when considering connecting to our network | We are collaborating with Northern Gas Networks, National Gas, and other key stakeholders to undertake a Situational Awareness Study to help us to better understand and mitigate the risks associated with the impact of a range of future scenarios, including blended and full hydrogen, on control room systems. | 2024 Jul: Familiarisation, Literature and Industry Review, Review and Assess, Develop and Validate Report; 2025 Oct: Build solutions based on robust approach on which to base future control room system and process design decisions
| Consumer insight on future energy solutions in their area | Tool to enable consumers to understand their future energy options speficifc to their area | The succesful Proof of Concept in Microsoft Fabric enabled us to demonstrate the possibility for such insight using demand data. The focus of these activities for the remainder of the price control period will be to break down energy plans created based on different scenarios, develop consumer energy solution scenarios and associated choices, and consider the development of an appropriate dashboard to support insights visualisation. | 2025 Feb: Proof of Concept; 2025 May: Develop consumer energy solution scenarios and associated choices and plan to develop dashboard to visualise future energy options
| Consumer Database Solution | New interoperable system to manage meter point and consumer demand data will enable real-time network management and make it easier to share data in formats and granularity required by stakeholders | Design and build completed, solution in UAT, go-live targeted for July 2025. Training completed for relevant employees in preparation for go-live. Old system to run in parallel for 1-3 months to support transition. | 2024 Sep: Scoping; 2024 Oct: Initiation; 2024 Nov: Design; 2025 Jan: Build and Test; 2025 Jul: Live
Technology | Data Lakehouse | Ensures that everyone in the organisation is working with the same, up-to-date information by centralising all data into a single repository. This eliminates discrepancies and enhances decision-making accuracy. This project will not only reduces storage costs but also simplifies data management and improves data quality. With a centralised system, we can enforce consistent data processing and business logic across the organisation, making it far easier for us to meet the data sharing needs of our stakeholders. In many cases we need to apply a different set of logic for external sharing compared to internal needs for running the business. A data lakehouse will enable this which also makes it an essential tool in achieving data interoperability. | Data architect appointed to the organisation allowing requirements definition to progress and enabling us to progress to writing an internal investment paper for this platform. This had been on hold pending this appointment. By leveraging an existing relationship with Microsoft, this saved both time and money by not requiring a new procurement event. Ongoing data migration activities to commence in January 2026. | 2024 Oct: Scoping; 2025 Feb: Proof of Concept; 2025 May: Requirements gathering; 2025 Jul: Investment Paper; 2025 Aug: Initiation; 2025 Sep: Build and Test; 2025 Dec: Live; 2026 Jan: Data migration
| Data Analytics & Reporting Platform | Enhanced ability to derive actionable insights from our data with which to make evidence-based decisions that will improve our operational performance and enhance the value we can create for our customers and communities | Data architect appointed to the organisation allowing requirements definition to progress, this had been on hold pending this appointment. Proof of Concept for Power BI completed as part of Fabric PoC. New target date for investment paper moved to July. | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Jul: Investment Paper; 2025 Aug: Initiation; 2025 Sep: Build and Test; 2025 Nov: Live; 2025 Dec: Data population
| Open Data Platform | - Integrate with our Data Catalogue so that metadata can be published and shared with the various datasets. - Simplify the publication and sharing of content from our Data Asset Register to different stakeholders with discrete access permissions as required. - Provide a mechanism for users to log of data quality issues, with the ability to respond with detail how these issues were, or will be, resolved; which in turn will offer us valuable insight into who is digesting our data and how it’s being used. - Integrate workflows aligned to our enhanced digital & data governance to monitoring and fulfilment of user data requests. - Reduce manual intervention and automate where possible, reducing delays in processing data requests. - Comply with Security, Privacy and Resilience (SPaR) best practice and the WWU IT Security standards. - Improve data quality through adherence to the Dublin Core Metadata standard and enhanced metadata management; datasets published for consumption should have associated metadata captured and stored that will allow effective change management for the publication of the dataset. | Data architect appointed to the organisation allowing requirements definition to progress, this had been on hold pending this appointment. New target date for investment paper moved to July. In the interim, data governance specialists supporting updates to our existing webpage for consumers to access available Open Data. | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Jul: Tender; 2025 Sep: Investment Paper; 2025 Oct: Initiation; 2025 Nov: Build and Test; 2026 Mar: Live
Ongoing improvements to existing webpage with available Open Data
| Data Catalogue | Transparency and awareness for data users on data held | Purview was demo'd as part of the Fabric PoC but more needs to be done to showcase the Data Map and Unified Catalogue functionality. This is technically dependent on Go/No Go decision on Lakehouse. Meanwhile, enterprise data landscape and criticality of data sources can be documented. | 2024 Oct: Scoping; 2024 Nov: Requirements gathering; 2025 Jul: Investment Paper; 2025 Aug: Initiation; 2025 Sep: Build and Test; 2026 Jan: Live
| Digital Applications | Suite of applications built in core systems to solve the problems for our data users. Will drive efficiency, saftey, better service and support decision making | We're continuing to identify and build value-add digital applications using Power Apps to drive efficiency and improve outcomes for our colleagues and end users. Examples include a Waste Tracking tool which records the pick-up of materials from vendors and delivery to sites, as well as the Personal Vibration Exposure Time (PVET) tracking tool migration to a new server plus initial scoping to adapt the tool to include sound usage. | 2024 Jul: Ongoing build and continuous refinement based on collection of user requirements
| Retire legacy apps | Eliminate technical debt as obsolete applications are replaced with new digital solutions | Dependent on delivery of new digital applications. | 2025 Jul: Formally retire as replacements delivered
People & Processes | Independent Data Maturity Assessment | Conducted a review of existing documentation and carried out interviews and surveying of WWU employees | Complete and recommendations made. Data Steering committee required focussed on delivering business outcomes through programme and workstreams. Review maturity over time. Head of Data recruitment (underway) will accelerate this. | 2024 Sep: Information gathering; 2024 Nov: Analysis; 2024 Dec: Final report delivered
| Building in-house expertise | Competent data teams to support and deliver against the needs of data users and wider stakeholders | Some key roles filled on a temporary basis by contractors. Large recruitment programme in mid-late 2025. Recruitment, internal role mapping and use of third parties is required to fill gaps in data competency. Review complete and actions underway but needs continuous focus. | 2024 Nov: Sign off operating model; 2025 Feb: Complete and advertise job descriptions; 2025 May: Interviewing and onboarding
| Conduct a Discovery which considers how photographic or video evidence could be used to inform Health and Safety | Potential to automate critical safety alerts through visual evidence with data science applied (if appropriate) | Flight monitoring, flying the pipelines, videos are watched by experienced staff. Just beginning to trial AI and machine learning as PoC. | 2024 Sep: Trial of technologies; 2025 Sep: Implementation if PoC successful
| Data Governance Policy Framework | Governance policies will ensure consistent and transparent data management practices across the organisation. By reducing ambiguity in roles and responsibilities, these policies will improve accountability and align WWU with regulatory frameworks, building trust with stakeholders. | Head of Data being recruited and governance-specific roles recommended. When permanent accountable and responsible individuals are in place this will be accelerated. | 2024 Sep: Develop Data Best Practice Maturity Roadmap; 2025 Jun: Data Policy Drafting & Governance working party set-up; 2025 Sep: Embed policy into BAU and conduct ongoing review of processes and policies
| Ownership and Accountability Model | Assigning clear roles and responsibilities for data assets will foster organisational accountability and promote proactive data management practices. By reducing operational risks and clarifying responsibilities, the model ensures better data-related decisions and strengthens the organisation’s ability to meet regulatory expectations. | Data R&Rs for the overarching programme have been structured and recruitment is underway for priority roles. Data owners have already been identified and this will be refined further during cataloguing. | 2025 Jun: Further refinement based on outputs of data cataloguing exercise; 2025 Sep: Embed ownership model and monitor for ongoing impact
| Data Quality Monitoring Framework | A data quality monitoring framework will provide real-time visibility into the accuracy, completeness, and timeliness of data, improving decision-making at all levels. By detecting and resolving data issues early, the framework reduces costs associated with poor-quality data and enhances stakeholder confidence in WWU’s data reliability. | Data quality analysis will be conducted via the Data Analytics & Reporting Platform. Go/No Go decision required on Fabric/Power BI. Responsbile data quality analyst to be identified. | 2025 Jun: Define KPIs; 2025 Aug: Develop reports based on critical data assets (using existing platform capability); 2025 Dec: Migrate reporting suite into Data Analytics & Reporting Platform and refine based on feedback
| Centralised Data Catalogue | A centralised data catalogue will act as a single source of truth, enabling easier data discovery and access for internal and external stakeholders. This will reduce duplication of effort, improve collaboration, and enhance the organisation’s ability to meet data sharing and usability standards. | Purview was demo'd as part of the Fabric PoC but more needs to be done to showcase the Data Map and Unified Catalogue functionality. This is technically dependent on Go/No Go decision on Lakehouse. Meanwhile, enterprise data landscape and criticality of data sources can be documented. | 2025 Mar: High-level functionalities demo'd in Purview as part of Fabric PoC; 2025 Jun: Develop Dublin Core-aligned metadata structure; 2025 Sep: Embed metadata structure in new data governance tooling
| Enhanced Access Control System | Strengthening access controls will ensure that data is only accessible to authorised users, reducing risks of data breaches and unauthorised access. Improved compliance with GDPR and other regulatory requirements will demonstrate WWU’s commitment to robust data handling practices, enhancing stakeholder trust. | Business side data source owners and IT systems of record owners are being identified to ensure a consistent approach is adopted across the enterprise IT landscape. A Universal Permissions project is underway to support our progress against these objectives. | 2025 May: Universal Permissions project in-flight to conduct permissions audit and draft access policies
| Enriched Disaster Recovery Protocols | Disaster recovery protocols will protect critical systems and data assets, ensuring resilience during disruptions. By reducing downtime and minimising financial impacts, these protocols will enhance stakeholder trust and demonstrate WWU’s preparedness to handle unexpected incidents. | Planned acitivities will improve visibility of risks and management of change. Risk mitigation and distaster recovery activities will be further refined as part of this review. | 2025 Jul: Review draft risk assessment and disaster recovery plans; 2026 Jan: Operational Simulations