| # Briefing Note 10: Plan Date Control |  |
| --- | --- |
| Version 1.0 January 2023 |  |

Table Of Contents

1)	Introduction	3

2)	FM144/FM166 – LP/MP Works not Exceeding 63mm PE diameter	3

3)	RO/NRO – Works Exceeding 63mm PE diameter	4

4)	Weekly Whereabouts	5

Introduction

Following receipt of design approval, the project can be planned. It is mandatory that the nominated GIRS Registered Company carrying out the works receives plan date approval.

Please note: Before works commence the IGT or UIP must carry out a final safety check by going to https://www.linesearchbeforeudig.co.uk/ and retrieving the latest utility plans. You can also go to https://www.wwutilities.co.uk/services/dial-before-you-dig/ for further information.

FM144/FM166 – LP/MP Works not Exceeding 63mm PE diameter

On approval of applicable design submissions, WWU will issue a FM144 63mm Authorisation Letter (FM144) / FM166 63mm Alteration Disconnection Authorisation Letter (FM166) to enable the customer to submit a plan date.

The customer must complete the FM144 / FM166 with the required plan dates, installers name and their EUSR number, and submit to Third Party Connections at least 3 working days before the works are due to be carried out.

Please Note - Third Party Connections will issue approval via email, the works cannot proceed if authorisation has not been received.

RO/NRO – Works Exceeding 63mm PE diameter

Following design approval for applicable projects, the Authorising Engineer must contact Network Control to log a Routine Operation (RO) or a Non-Routine Operation (NRO).

As outlined in the Final Connections Agreement, an RO should be submitted at least 5 working days before the works are scheduled to begin and an NRO should be submitted at least 10 working days before the works are scheduled to begin.

WWU will give Provisional Clearance to Proceed as soon as possible following receipt of the RO or NRO. Please note that the Authorising Engineer must contact Network Control 48 hours before work proceeds and on the morning of the works, to enable WWU to run a final conflict check. Should an emergency arise, WWU maintain the right to withdraw clearance to proceed in line with WW/PM/SCO/4 and WW/PM/SCO/5.

Weekly Whereabouts

When the application is submitted (either via quotation request or fast track) the IGT/UIP is required to provide the name of the GIRS qualified company that will be carrying out the works. Should this change, it is the responsibility of the IGT/UIP to inform WWU. This can be done via an email to gtuip@wwutilities.co.uk

Before the close of play on a Friday, the GIRS registered company must submit a completed Weekly Whereabouts sheet for the following week and send it to gtuip@wwutilities.co.uk. If no works are to be carried out the following week, and email stating this will suffice.

Please note: The Weekly Whereabouts is required in addition to the FM144/FM166/RO/NRO.