| # Briefing Note 14: GL5 Process |  |
| --- | --- |
| Version 1.0 January 2023 |  |

Table of Contents

1)	Introduction	3

2)	GL5 Process Outline	3

2.1) Stage 1	3

2.2) Stage 2	4

2.3) Stage 3	4

2.4) Stage 4	5

3)	Competent Design Authority Register (CDAR)	5

4)	Electronic Signatures	5

5)	Design Submission	5

Introduction

This Briefing Note provides third parties with guidance on the Wales & West Utilities (WWU) procedure for new works, modifications and repairs to WWU gas assets, in line with the requirements under IGEM Standard T/PM/GL/5.

Please note all GL5 correspondence should be sent to GL5request@wwutilities.co.uk and cc. gtuip@wwutilities.co.uk; maureen.leyshon@wwutilities.co.uk

GL5 Process Outline

2.1) Stage 1

The customer sends the signed IP Quotation to gtuip@wwutilities.co.uk

Third Party Connections will process this acceptance and issue an Acceptance Acknowledgement Letter and the GL5 Initiation Form

The Initiator must complete, date and sign the Initiation Form and return to GL5request@wwutilities.co.uk and cc. gtuip@wwutilities.co.uk; maureen.leyshon@wwutilities.co.uk

The Initiation Form has to be sent to WWU at least 30 working days before the connection date.

2.2) Stage 2

- Upon receipt of the Initiation Form, the GL5 will be registered by WWU using the information provided.

- The GL5 pack will then be emailed to the customer. This pack will contain Forms Part A to F, plus supporting Appendices.

- Once the pack is received, the Initiator needs to complete the following:

  - Check details on Part A are correct.

  - Complete relevant Appendices and make sure that each form is signed and dated by the Initiator.

  - Arrange for the Design Manager to confirm Design Approval by electronically signing/dating 1st Part of Form Part B.

  - Compile Supporting Documentation Folder. If a new connection, this has to include a copy of the PSSR line drawing identifying the connection point on to the WWU Network.

- The completed pack must be returned to WWU at least 20 working days before the planned connection date for Design Appraisal and User Acceptance Approval.

2.3) Stage 3

- WWU will review the design and where applicable, complete and issue a Technical Appraisal Form.

- Once Design and Acceptance Approval are granted, WWU will return the signed forms to the customer and work can commence.

2.4) Stage 4

- Upon completion of the works, the Installer and Initiator need to sign off Forms Part D and E, and return the whole pack to WWU

- Form Part F will be completed by WWU’s Asset Integrity team.

Competent Design Authority Register (CDAR)

When third party works require appraisal and approval under GL5, the individuals undertaking the different elements of third party design approval, appraisal, construction and commissioning must be on the “Competent Design Register”, which is maintained by a “Competent Design Authority”, currently DNV (Det Norske Veritas).

Should the third party wish to carry out their own Design Appraisal, a copy of the Appraiser’s Certification is required along with the rest of the GL5 pack.

Electronic Signatures

To enable WWU to ensure that the GL5 has been reviewed/approved by the Competent Person named on the forms, an email is required from the relevant party confirming that they have signed the documents.

Design Submission

Where a Design Submission has been previously been submitted to Third Party Connections, following the approval of the GL5 the Design Submission will be processed by Third Party Connections.

Alternatively, the Design Submission can be submitted at this stage.